## Overview
🌸 Pumdoki Delivery Dashboard
Updated September 9, 2026. Private R2 photo/video flow verified with real cloud storage. Next: founder reviews the working local upload/publish flow. LLC awaits Maryland approval. Record counts are not launch readiness.
Current focus | [7 empty] | Next founder decision
Phase | P05 — First functioning content flow | [6 empty] | R2 connection verified: safe photo/video upload, private drafts, publish/member read and removal. Public Access Disabled confirmed in Cloudflare. Next: founder reviews this working local flow. No hosted deployment or processor approval is claimed.
Work | Review the working local R2 content flow
Workflow | One task at a time
Scope | Payment method unresolved. Subscriptions, PPV, Store, Connect, chat and tipping remain launch scope; old Oasis cancelled.
Evidence | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md | [6 empty] | Funding notes: founder reports a $1,800 monthly ceiling; this is not lump-sum cash or funded runway. Existing $1,000–$5,000 cash assumptions remain until clarified. See Launch Budget.
Execution summary
Execution records |  | Done |  | In Progress |  | In Review |  | Blocked |  | Not Started |  | Record progress
156 |  | 32 |  | 53 |  | 2 |  | 1 |  | 66 |  | 20.51%
Phase roadmap
Phase | PLAN phase | Phase State | Maturity | Records Done | Execution Records | Record Progress | In Progress | In Review | Blocked | Not Started | Current focus | Next gate | Evidence
P00 | Baseline, tracker, and scope control | Partially Complete | Integrated | 6 | 6 | 100% | 0 | 0 | 0 | 0 | Maintain the PLAN-aligned execution tracker, decision register, review queue, and daily debrief history. | Assign and maintain owners and next-check dates for remaining active decisions; preserve legacy records. | https://github.com/QK-Connoisseur/PDoki/pull/13
P01 | Repository and frontend foundation | Complete | Integrated | 4 | 8 | 50% | 4 | 0 | 0 | 0 | Maintain routing, shared shell, fixtures, CI, error states, and code splitting. | No active gate; preserve regression coverage as product phases integrate real data. | https://github.com/QK-Connoisseur/PDoki/pull/2
P02 | Backend and database foundation | Partially Complete | Backend Implemented | 4 | 16 | 25% | 7 | 0 | 0 | 5 | PR #13 published the application-owned PostgreSQL worker foundation and fixed non-secret canary; no product flow uses it. | Keep Phase 2 partial: staging, restore/backups, monitoring, Redis/shared throttling, general idempotency, and deployment remain open. | https://github.com/QK-Connoisseur/PDoki/pull/13
P03 | Authentication, roles, and settings | Complete | Integrated | 6 | 8 | 75% | 2 | 0 | 0 | 0 | Maintain the founder-approved reduced core auth/account-security scope. | Later Settings domains move only with their dependency phases. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#7-phase-3--authentication-roles-and-settings
P04 | Legal, trust, and creator onboarding | Partially Complete | Backend Implemented | 5 | 35 | 14.29% | 18 | 0 | 0 | 12 | Slices 1–4 published; operations dormant. Maryland approval pending. Initial CCBill reply retained; proposed follow-up cancelled. Founder/provider work now accompanies each functional code slice. | Resolve business/legal/provider prerequisites in sequence. G1–G12 apply to operations activation, not all synthetic local product work. | https://github.com/QK-Connoisseur/PDoki/pull/15
P05 | Media pipeline and content model | Partially Complete | Backend Implemented | 1 | 10 | 10% | 4 | 2 | 0 | 3 | Safe photo/video flow now uses private R2 storage. Cloud upload/read, private drafts, publish/feed, ranges, restart persistence and removal are verified. Test accounts only. Hosted review deployment and production media controls remain open. | Founder reviews the working local R2 upload/publish flow for this slice. No new signup, paperwork or payment task. Real identity, adult uploads and payments remain disabled. Full P05 exit, deployment and processor approval remain open. | HANDOFF.md
P06 | Payments, subscriptions, tipping, and PPV | Partially Complete | UI Prototype | 0 | 16 | 0% | 3 | 0 | 0 | 13 | Provider/site preparation is in progress: CCBill Sales replied, safe-content/R2 milestone is verified and policy drafting is commissioned. Payment backend, webhooks and paid entitlements have not started. | Continue functioning-site slices; password protection is permitted for later review. Founder reviews the current local flow. Return to CCBill when review-ready; define the supported payment method before integration. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md
P07 | Core end-to-end vertical slice | Blocked | N/A | 0 | 1 | 0% | 0 | 0 | 1 | 0 | Core journey still needs creator, content/access and operations controls. Apply payment dependencies to the chosen beta method. | Continue safe test flows. Define the beta payment model with its slice; any paid flow requires processor confirmation, entitlements, auditable earnings and reconciliation. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#11-phase-7--core-end-to-end-vertical-slice
P08 | Feed, social actions, Store, and Connect | Partially Complete | UI Prototype | 4 | 10 | 40% | 6 | 0 | 0 | 0 | Feed, Store and Connect remain launch scope (online/price/language discovery). Your Activity /activity UI is an explicit example-data preview; real member history remains pending. | Integrate content/access, service/order and beta payment rules. Connect Your Activity to authenticated P05/P06/P07 data. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#12-phase-8--feed-social-actions-store-and-connect
P09 | Real-time messaging and notifications | Partially Complete | UI Prototype | 1 | 4 | 25% | 2 | 0 | 0 | 1 | Real-time direct chat remains required at launch. Prototype bell/activities do not establish persisted product notifications. | Approve conversation/message persistence and WebSocket authorization design. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#13-phase-9--real-time-messaging-and-notifications
P10 | Creator dashboard | Partially Complete | UI Prototype | 0 | 1 | 0% | 1 | 0 | 0 | 0 | Large UI prototype exists; backend data, actions, and financial reconciliation are absent. | Connect dashboard modules only after their source domains are implemented. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#14-phase-10--creator-dashboard
P11 | Admin and moderation | Blocked | Backend Implemented | 0 | 14 | 0% | 2 | 0 | 0 | 12 | Dormant operations source remains parked. The next planned P05 test-content flow pairs storage decisions with implementation. No deployment, live payment or identity activation is implied. | Evaluate provider, restricted hosting, MFA/recovery, session, permission, audit and deployment controls when activating real operations. | https://github.com/QK-Connoisseur/PDoki/pull/15
P12 | Oasis replacement concept (post-launch) | Deferred | UI Prototype | 0 | 2 | 0% | 0 | 0 | 0 | 0 | Old Oasis/Drimy game CANCELLED on September 6, 2026. Name may be reused for day/friend streaks and playful adult language learning. | No launch gate. Define the replacement after launch; opt-in roasting and language concept remain unimplemented. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md
P13 | Internationalization and accessibility | Partially Complete | UI Prototype | 0 | 2 | 0% | 1 | 0 | 0 | 1 | Scattered responsive/accessibility work exists; bilingual core flows and a formal audit remain open. | Extract UI copy and scope English/Spanish plus keyboard, focus, contrast, screen-reader, and reduced-motion work. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#17-phase-13--internationalization-and-accessibility
P14 | QA, security, private beta, and launch | Partially Complete | Integrated | 1 | 22 | 4.545% | 3 | 0 | 0 | 18 | CI/E2E foundations and the deterministic promotion clock fix are published; product E2E, security drills, beta, and launch gates remain open. | Verify applicable creator, content, security, recovery and support controls for beta. Paid flows also need processor and payment controls. | https://github.com/QK-Connoisseur/PDoki/actions/runs/32535922437
How to use this workbook
1 | One functional slice at a time. R2 setup and safe-media integration are verified. Next: founder reviews the working local upload/publish flow to close this slice. CCBill follow-up stays cancelled; live sensitive use remains unavailable. | 2 | Use Delivery Tracker for canonical execution status. | 3 | Use Phase Roadmap for evidence-based phase state and exit gates. | 4 | Use Daily Log for each meaningful work-session debrief. | 5 | Master Tracker remains the preserved legacy source.
Review rule | Open PR/review artifact → In Review. Green CI does not equal Done. | Done rule | Accepted and verified defined scope; not automatically production-ready. | Phase 2 | PR #13 is merged and CI-verified; the fixed canary foundation is Done while Phase 2 remains partial. | Phase 4 | Slices 1–3 are published; further operations work is parked. Activation controls remain unevaluated. | Post-MVP | Still tracked in Backlog and POST phase.
Legacy preservation | No legacy task, note, backlog item, assumption, or expense value was deleted. | Expense QC | Year 1 arithmetic corrected to $2,366; original $1,713 retained. Use Launch Budget for current estimates. | Daily cadence | Update active/review/blocked rows after work; review priorities weekly. | Evidence | Use PR, commit, CI, or architecture URLs—not copied technical test matrices.
Source of truth | PLAN.md = phase architecture; Delivery Tracker = current execution; HANDOFF.md = active technical evidence. | Metric rule | Record progress counts preserved/current records; Phase State is the canonical PLAN judgment. | Published base | See HANDOFF.md for verified current branches | Latest merge | Slice 3: PR #15; Slice 4: PR #17 merged in dev 56cb0ad | Next founder task | Founder reviews the working local R2 upload, draft, publish and removal flow.

## Master Tracker
🌸 PUMDOKI — Master Build Checklist
A space for creators, members, and real interaction.
Phase / Item | Description | Status | Notes
🎯 PHASE 1 — Strategy & Scope
Define core value proposition | Lock the core promise for creators, members, and interaction. | ✅ Done | Positioning: 'A space for creators, members, and real interaction.'
Lock MVP scope | Subscriptions-first, NSFW at launch. Confirm what is excluded from v1. | ✅ Done | MVP scope set.
Document post-MVP delays | Keep live streaming, advanced chat, tipping, PPV, analytics, rec engine, extra themes, gamification out of MVP. | ✅ Done | MVP vs later items distinguished.
Convert roadmap into phase plan | Break work into design, build, test, beta, and launch phases. | ✅ Done | Dependency-ordered PLAN.md is established and current through the merged PR #1–#3 baseline; tracker reconciliation is now ongoing maintenance.
Set launch KPIs | Define targets: creators onboarded, paid members, conversion, retention, bug rate. | 📋 Not Started | Needed before beta/public launch.
⚖️ PHASE 2 — Legal & Compliance
Draft Terms of Service | Prepare terms governing platform use, NSFW content rules, user responsibilities, dispute resolution. | 🔄 In Progress | Must exist before launch.
Draft Privacy Policy | Data collection, cookies, third-party sharing, CCPA/GDPR rights, data retention. | 🔄 In Progress | Privacy layers discussed; formal draft needed.
Draft Community / Platform Rules | State permitted and prohibited activity clearly for creators and members. | 🔄 In Progress | Required for moderation consistency.
Draft Acceptable Use Policy | No minors, no non-consensual content, no illegal material, no harassment. | 🔄 In Progress | Separates from ToS for clarity and enforcement.
Create DMCA Policy & Takedown Process | Copyright reporting form, designated agent, response procedures (17 USC §512). | 🔄 In Progress | Required for content platforms.
Implement 18 USC §2257 Recordkeeping | Maintain age verification records for performers in sexually explicit content. Display §2257 compliance statement. | 🔄 In Progress | Federal requirement for adult content platforms.
Draft Cookie Policy & Consent Banner | Disclose cookie usage, purposes, opt-out. Implement consent UI (required for GDPR/ePrivacy). | 🔄 In Progress | Required for EU visitors; best practice globally.
Implement GDPR Compliance | Right to access, deletion, data portability, consent management, DPA with processors. | 🔄 In Progress | Required if serving EU users.
Implement CCPA/CPRA Compliance | 'Do Not Sell' opt-out, privacy notice for CA residents, data deletion requests. | 🔄 In Progress | Required if serving California users.
Prepare Payment Provider Compliance Package | Document policies/controls required by CCBill and Epoch for merchant onboarding. | 🔄 In Progress | CCBill replied: functioning online site needed; password protection allowed. Site/policy preparation underway.
Draft Creator Agreement / Payout Terms | Creator obligations: content ownership, tax (W-9/W-8BEN), payout terms, prohibited content. | 📋 Not Started | Needed before creator onboarding.
Implement Visa/Mastercard BRAM Compliance | Meet Brand Risk and Acquirer Monitoring requirements for adult merchants. | 📋 Not Started | Card network requirement for adult sites.
Finalize Trademark Filing Plan | Decide classes (IC 009, 035, 042), timing and filing sequence for 'Pumdoki'. | 🔄 In Progress | Trademark timing/classes already considered.
Finalize Domain Management | Secure primary domains and variants (.com, .net, etc.). | 🔄 In Progress | Domain strategy already considered.
Address MD Business Registration Privacy | Manage privacy concerns — MD biz records may expose personal identity linked to NSFW platform. | 🔄 In Progress | Entity not filed. Evaluate Wyoming and other privacy/no-individual-income-tax candidates with an attorney and CPA; account for foreign qualification where the founder operates.
Implement Accessibility Basics (ADA/WCAG) | Alt text, keyboard navigation, contrast ratios, screen reader compatibility. | 📋 Not Started | Best practice; reduces legal risk.
Draft Anti-Human Trafficking Policy | Prohibit trafficking, exploitation, coercive content. Include reporting mechanisms and creator guidance. | 🔄 In Progress | Included in Suzanne Lawyer’s purchased $1,100 bundle. Draft delivery, review and approval pending.
Draft Non-Consensual Content Policy | Standalone policy prohibiting NCII. Define removal process, reporting path, and creator obligations. | 📋 Not Started | Must be its own doc for payment processor and Visa/MC BRAM review.
Implement US Take It Down Act Compliance | Written policy + removal workflow for non-consensual intimate images. Must action valid removal within 48 hours. | 📋 Not Started | Federal law signed 2025. Non-compliance is a federal offense.
Draft Law Enforcement Request Policy | Define process for handling government and LEA data requests — disclosure, legal basis, user notification. | 📋 Not Started | Commonly reviewed during CCBill/Epoch onboarding.
Draft Appeals Policy | Documented process for creators and members to appeal content removals, account suspensions, or payment holds. | 📋 Not Started | Needed before creator onboarding begins.
Draft Complaint Policy | Formal intake process for user complaints beyond DMCA — billing disputes, harassment, platform conduct. | 📋 Not Started | Best practice globally; supports EU DSA/P2B compliance.
Draft Anti-Spam Policy | Rules governing creator messaging to members, platform notifications, and marketing emails. | 📋 Not Started | Needed before the email/notification system goes live.
Draft Platform-to-Business (P2B) Terms | EU P2B regulation disclosure for creators — ranking criteria, access termination conditions, dispute options. | 📋 Not Started | Conditional on EU launch scope. Low effort to draft.
🎨 PHASE 3 — Brand & Design
Finalize brand aesthetic & color system | Confirm pink / sakura visual direction and supporting palette. | ✅ Done | Brand direction established.
Finalize logo / wordmark | Lock minimal premium wordmark. Symbol: heart + sakura petal + heartbeat + rounded sans-serif. | 🔄 In Progress | Direction exists; final asset lock not confirmed.
Finalize homepage messaging | Polish hero copy, value prop, marketing text. Avoid 'Softer'; feel inclusive, not creator-first. | 🔄 In Progress | Draft messaging exists; final copy not confirmed.
Define creator theme ladders | Floral: Petal→Bloom→Sakura→Golden Sakura→Eternal Sakura. Ember: Ember→Ignite→Flare→Inferno→Eternal Flame. | ✅ Done | Theme ladder concepts defined.
Build reusable design system | Buttons, cards, tabs, modals, badges, pricing modules, feed cards, locked-content previews. | 🔄 In Progress | Implied by active UI/front-end development.
Finalize responsive / mobile layouts | Ensure primary flows work cleanly on mobile and desktop. | 🔄 In Progress | Responsive work remains active. A session-aware branded 404, route-level code splitting, and an in-flow dismissible verification reminder are merged and CI-covered on desktop/mobile paths.
Implement Midnight City theme | Second free theme alongside Sakura Kiss. Blue city rooftops with static desktop/mobile JPG backgrounds. Settings Appearance chooser stores the preference in this browser. | ✅ Done | Published in 0f01961 (#19). Theme switch/restore and static assets are tested. Account sync remains separate future work.
Design Founding Creator / Member badge program | Define badge visuals, eligibility window (first N users or date window), locked-in fee reduction for Founding Creators, badge display on profiles and posts. | 📋 Not Started | First 500 creators get permanent Founding Creator badge + reduced platform commission. First 500 members get Founding Member badge + discount. Drives early community loyalty.
🏗️ PHASE 4 — Backend & Infrastructure
Define AWS architecture | EC2/ECS for app, RDS PostgreSQL for DB, Cloudflare R2 for media storage/CDN. | ✅ Done | AWS (app/DB) + Cloudflare R2 (media) confirmed.
Set up Cloudflare R2 media storage | Private safe-sample R2 bucket and API integration verified. Signed delivery, CDN caching and production storage lifecycle/recovery remain pending. | 🔄 In Progress | Safe PNG/MP4 uploads, private reads, restart/removal and browser checks passed. Adult-business acceptance unconfirmed.
Define RDS PostgreSQL schema | Model users, creators, posts, subscriptions, plans, transactions and moderation. | 🔄 In Progress | Local PostgreSQL/Prisma includes User, Session, append-only AcceptanceRecord, VerificationToken, UserPreference, CreatorApplication, creator-policy acceptance, and constrained successful-transition review evidence. Remaining product domains and production RDS deployment are pending.
Set up local / staging / prod environments | Separate environments, secrets handling, .env management. | 🔄 In Progress | Local validated environments plus Docker PostgreSQL/Mailpit exist. PR #3 adds non-secret staging/configuration/verification templates only; staging and production infrastructure, credentials, private origin, and live verification remain pending.
Define API structure | Map endpoints: auth, content, subscriptions, payments, moderation, admin, notifications. | 🔄 In Progress | Implemented /api/v1 health/readiness, auth/email, /me, protected Settings/session, and member creator-application flows. The creator-review router remains deliberately unmounted and requires an operations verifier; later product domains remain pending.
Implement logging & monitoring | Error tracking, structured logs, operational visibility (CloudWatch, Sentry). | 🔄 In Progress | Structured Pino request logging, request IDs, and secret-header redaction are implemented. PR #3 adds a provider scorecard/runbook only; monitoring integration, alerts, retention decisions, and live evidence remain pending.
Implement backups & recovery plan | Automated RDS snapshots, R2 versioning, disaster recovery. | 📋 Not Started | Required for production readiness.
Add rate limiting & abuse protection | Anti-scraping, anti-spam, brute-force protection, credential abuse. | 🔄 In Progress | Global per-IP limits plus bounded in-memory login and email-request throttles are implemented. Redis-backed multi-instance protection remains pending.
Set up CI/CD pipeline | Automate testing and deployment from Git branches to staging/production. | 🔄 In Progress | CI runs formatting, lint, web/API tests and builds, migrations/seed, private-admin build, and real-stack Playwright with read-only token permissions and bounded timeouts. PR #1–#3 passed reviewed-head CI; deployment automation remains pending.
Configure SSL/TLS & domain DNS | HTTPS everywhere, DNS records, certificate management. | 📋 Not Started | Required for production.
🔐 PHASE 5 — Accounts, Auth & Roles
Implement account creation & login/logout | Create working auth flows, not just screens. | ✅ Done | Slice 3 connects registration, login, logout, and authenticated route restoration to the live API.
Implement creator/member/admin roles | Role-based permissions and access boundaries. | ✅ Done | MEMBER/CREATOR route gates and backend role checks are implemented. The public web app has no /admin route; an ADMIN public session is not operational authentication and cannot activate the dormant review router.
Implement session management | Signed-in state, token/session renewal, logout behavior. | ✅ Done | HttpOnly-cookie sessions restore through /me, renew on a bounded sliding window, support logout/logout-all, and can now be listed and individually revoked from protected Settings. Sensitive account changes revoke other sessions.
Build onboarding flows | First-run setup for creators (incl. theme selection: Floral/Ember) and members. | 🔄 In Progress | A verified MEMBER can submit one persisted creator application; it remains PENDING with identity NOT_STARTED and no role promotion or Dashboard access. Member first-run setup, theme choice, identity/tax/banking intake, and operational approval remain pending.
Add 18+ entry gate & age verification | Consent gating and age/compliance checks at platform entry. | 🔄 In Progress | Registration records append-only age attestation and versioned Terms/Privacy acceptance; verified email gates creator-application submission. Entry-gate UI and actual identity/age verification remain pending.
Implement email verification | Require email confirmation for new accounts. | ✅ Done | Slice 3 provides verification screens and Mailpit-backed confirmation. Slice 4B adds authenticated email change, invalidates stale links, requires reverification, and preserves only the current session.
Implement password reset flow | Secure forgot-password and recovery process. | ✅ Done | Slice 3 provides reset request/confirmation and global revocation. Slice 4B adds current-password-confirmed password change, reset-token invalidation, and other-session revocation.
💻 PHASE 6 — Frontend & UX
Build homepage (logged-in feed) | Implement the main logged-in home experience with heart story rail and Following/For You tabs. | ✅ Done | Feed page designed with heart rail and tab system. Functional layout confirmed.
Build landing page | Public-facing marketing/conversion page for new visitors. | 🔄 In Progress | Auth/landing split screen complete. Raining hearts animation working. +18 checkbox present.
Build creator profile pages | Public creator profiles with plans, content previews, tier display, services tab, highlights. | 🔄 In Progress | Profile page designed. Services tab, heart highlights, subscribe button visible.
Build feed / discovery page | Hybrid discovery feed: For You + Following tabs, heart story rail. | ✅ Done | Heart rail + Following/For You hybrid implemented in design.
Build subscription / pricing page | Tier display: Standard (Doki 1–3), Premium (Super Doki 1–2), Ultimate (Doki Legend). | 🔄 In Progress | Part of the active front-end build.
Build login / signup screens | Account entry screens for creators and members. | ✅ Done | Live validated API login/signup/logout plus forgot/reset/verify flows are published. Registration was redesigned, verification reminders no longer overlay protected content, and deep-link restoration/session-aware recovery are CI-covered.
Implement story rail / For You model | Translate the interaction/feed architecture into actual UI behavior. | ✅ Done | Heart rail + Following/For You hybrid implemented in design.
Implement locked-content previews | Teasers and premium access states in cards and posts. | 🔄 In Progress | Locked preview UI exists; backend entitlement and protected media delivery remain.
Implement membership tier modules | Doki / SuperDoki / Doki Legend plan modules on creator pages. | 🔄 In Progress | Tier visuals exist. Launch tiers will be standardized; exact rules and backend enforcement remain.
Build Store page | Pumdoki Store front-end (Git branch: Store). | 🔄 In Progress | Launch-critical. UI prototype exists. Target four noticeable YouTube-like medium thumbnails on common large desktops, with more columns on wider screens.
Build Connect page | Social discovery front-end for session bookings (E-Chat, Voice Call, Video Call, Game With Me). | 🔄 In Progress | Launch-critical. UI prototype exists. Requires service configuration, availability, payment rules, cancellation, reviews and disputes.
Build Chat UI | Real-time direct messaging using authenticated WebSockets. Advanced group/chat features remain post-MVP. | 🔄 In Progress | Chat UI prototype exists. Persistence, WebSocket authorization, reconnect, read state, reporting, and rate limits are pending.
Implement NSFW +18 content toggle | User preference to hide or show explicit 18+ content across onboarding, Settings, feeds, search, Store, and Connect. Default hidden. | 🔄 In Progress | Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. Onboarding and server-side feed/search/Store/Connect enforcement remain pending.
Build settings page | Account info, password change, notification preferences, theme toggle (Sakura Kiss / Midnight City), NSFW content toggle, payment/billing section. | 🔄 In Progress | Protected Settings implements display name, email/reverification, password, active sessions and explicit-content preference. Theme selection is implemented browser-locally. Account theme sync, real notifications/billing, export and deletion remain pending.
Build help / support page | Basic FAQ page with accordion answers + simple contact/support form routed to founder inbox. | 📋 Not Started | Plain and functional for MVP. Expands post-launch.
Build 'Your Activity' page | P08 member history: liked posts, purchases, subscriptions and payment history. UI preview first; account-backed events follow. | 🔄 In Progress | Example-data /activity UI with search/filters and sidebar/header links. Real account API and persistence pending.
Improve Create Post ('Moments') modal | Replace generic 'What's on your mind?' with Pumdoki-voice copy. Add locked/subscriber-only content state. Improve layout and brand feel. | ✅ Done | Basic modal exists. Needs Pumdoki language, locked content toggle, and improved visual polish.
Improve side navigation drawer | Make drawer slightly larger and use darker, more vibrant colors. Currently blends too much into the background — needs presence like Instagram's nav. | ✅ Done | Drawer functional but visually weak. Increase icon size, darken colors, improve active state.
Fix chat: offline avatar + notification badge | Show creator offline avatar/indicator when creator is offline. Show unread notification badge on minimized chat. Currently missing both. | ✅ Done | Chat functional but missing offline state and notification badge on minimized view.
Build creator dashboard UI | Creator-facing analytics dashboard: revenue chart, active subscribers, profile visits, live activity feed, revenue by source, top performing posts, top fans, quick actions. | 🔄 In Progress | Large UI prototype exists. Backend data, actions, reconciliation, and tests remain. Live Streaming stays disabled post-MVP.
Improve landing page posts visuals | Add a checkmark, a follow buttom, re-arrenge For You / Following and flip sides, add logic to For You (X inspired), | ✅ Done | Post visual already in place. Need to add more features and complex logic to the For You page
📸 PHASE 7 — Content & Media
Define post / content model | Creator posting, visibility flags (public/subscriber/tier-locked), member access rules. | 📋 Not Started | Core content object needs build.
Build media upload pipeline | Image/video upload → Cloudflare R2 storage → signed URL delivery. | 📋 Not Started | Launch-critical capability.
Define public vs private asset rules | Separate teaser, paid, and internal assets with signed URL gating. | 📋 Not Started | Needed for secure access gating.
Implement media optimization | Compress/transcode images and video (thumbnails, adaptive quality). | 📋 Not Started | Needed for smoother UX.
Implement watermarking / content protection | Visible + invisible watermarks to reduce re-sharing risk. | 📋 Not Started | Protection planning in scope.
Build moderation review flow | Flagged items reviewed and actioned by admin. | 📋 Not Started | Required for platform operations.
💰 PHASE 8 — Payments & Monetization
Integrate CCBill (primary processor) | Set up merchant account, API integration, webhook handling, subscription billing. | 🔄 In Progress | Sales replied; review site is being built. Merchant approval, API/webhooks and billing remain unimplemented.
Integrate Epoch (cascade fallback) | Set up Epoch as secondary for transactions CCBill declines. | 📋 Not Started | CCBill site prep underway. Epoch outreach, account approval and integration remain unstarted.
Build payment cascading logic | Route failed CCBill transactions automatically to Epoch before returning decline. | 📋 Not Started | CCBill site prep underway. Cascade needs written account-specific confirmation from both processors.
Implement recurring subscription billing | Create the actual subscription/payment flow through CCBill/Epoch. | 📋 Not Started | CCBill site prep underway. Billing awaits agreed payment flow, processor approval and trusted payment events.
Build renewal / cancel logic | Recurring billing state changes, grace periods, cancellations. | 📋 Not Started | Needed for subscription lifecycle.
Tie access gating to subscription status | Grant/revoke content access based on active payment state and tier. | 📋 Not Started | Critical premium access control.
Define creator payouts flow | Payout cadence (weekly/biweekly), ledger logic, minimums, admin handling. | 📋 Not Started | Needed once monetization is live.
Define platform commission model | Fee structure: platform take rate, creator share, member economics. Founding Creator exception rate must be defined. | 📋 Not Started | Founder decision pending. Model 20/25/30% platform fees against actual processor fees before promising a creator split.
Implement chargeback & dispute workflow | Track chargebacks from CCBill/Epoch, alert admin, manage dispute responses. | 📋 Not Started | CCBill site prep underway. Dispute workflow awaits processor rules/events and authorized operations.
Plan crypto payment integration | Research USDT/BTC path. Evaluate self-hosted vs third-party (NowPayments, PayRam). | 📋 Not Started | Deferred; planned as future payment rail.
🛡️ PHASE 9 — Admin Dashboard & Moderation
Build private operations application | Deploy a separately hosted private operations app; do not expose /admin in the public Pumdoki web app. Enforce ADMIN permissions in the API and apply separate operational access controls. | 🔄 In Progress | An independently buildable apps/admin shell, public /admin removal, a dormant injected-verifier API seam, and a non-secret readiness packet are merged. No deployed private origin, production verifier, hardware-backed assurance, operator provisioning, origin/CSRF controls, restricted DB grants, or usable review UI exists; G1–G12 are NOT EVALUATED.
Build admin overview / operations page | Operational snapshot: total users, new signups today, active creators, revenue (gross/net), payout queue, content mod queue count, active flags. | 📋 Not Started | First page you see when logging into admin. Keeps you informed at a glance.
Build users & creators admin table | Searchable table of all accounts. Filter by role (member/creator/admin). View status, join date, spend, earnings. Actions: warn, suspend, ban, verify. | 📋 Not Started | Core operational tool. Needed for day-1 operations.
Build creator verification & onboarding queue | Review incoming creator applications. View submitted ID documents. Approve or reject. Log decision with reason. Trigger creator onboarding email. | 🔄 In Progress | Application submission/persistence and dormant server-side NEEDS_INFORMATION/REJECTED transitions with successful-transition evidence are merged. No queue/list/detail UI, ID/selfie intake, APPROVED, role promotion, reviewer deployment, notification, or creator publishing exists.
Build content moderation queue | Queue of all flagged content sorted by severity. Actions: approve, remove, warn creator, escalate. Show content type, creator, flag reason, reporter. | 📋 Not Started | Especially important for NSFW operations. Will be high-volume once platform grows.
Build reports handling workflow | Route user/content reports into admin triage with severity levels (High / Medium / Low). Show open report count, type, and age. | 📋 Not Started | Needed for safety and operations.
Build payments & payouts admin view | View all transactions, subscription events, payout queue. Manually trigger or block payouts. View CCBill/Epoch transaction IDs. Filter by date, creator, status. | 📋 Not Started | CCBill site prep underway. Admin view awaits payment/payout data and private-operations controls.
Build chargeback alert dashboard | View verified processor chargeback events, calculate rates, apply confirmed account-specific alert thresholds and log authorized dispute responses. | 📋 Not Started | CCBill site prep underway. Dashboard awaits verified dispute events and account-specific alert thresholds.
Build Founding Badge admin management | View list of Founding Creators and Founding Members. Track how many slots remain. Assign or revoke badge manually if needed. Show badge count against cap. | 📋 Not Started | Required to manage the founder badge program. Badge count cap enforced here.
Build admin platform settings panel | Configure: platform commission rate, Founding Creator commission rate, NSFW content flags, feature flags (enable/disable features), payout minimums, maintenance mode. | 📋 Not Started | Gives you control over live platform behavior without code deploys.
Implement 2257 compliance records admin | View and manage age verification records submitted by creators. Link each creator to their ID verification doc. Must be accessible on demand for compliance audits. | 📋 Not Started | Federal requirement. Must be in place before any adult content goes live.
Implement audit log | Track all admin actions with timestamp, admin user, action type, and affected entity. Immutable log — no deleting entries. | 📋 Not Started | The merged creator-review event records successful non-approval transitions at application level, but it is not a complete immutable operations audit. The global audit log, restricted audit destination, retention, and operational evidence controls remain unimplemented.
📊 PHASE 10 — Analytics, Support & Notifications
Define analytics event tracking | Track signups, subscriptions, content views, conversions, churn signals. | 📋 Not Started | Needed before beta/public launch.
Build launch KPI dashboard | Lightweight internal reporting view for admin. | 📋 Not Started | Needed to monitor launch health.
Set up support / contact workflow | Route issues to a manageable inbox (email-based initially). | 📋 Not Started | Needed for operational readiness.
Create FAQ / help center content | Common setup, billing, and policy answers. | 📋 Not Started | Useful before public launch.
Implement notifications / email system | Transactional emails (welcome, billing, reset) and platform notices via SES or Resend/Postmark. | 🔄 In Progress | Provider-neutral console/SMTP delivery, local Mailpit, and verification/password-reset messages are implemented. Production provider selection, adult-business fit, deliverability/authentication, billing/moderation/booking mail, and platform notifications remain open.
🚀 PHASE 11 — Creator Ops & Go-To-Market
Recruit initial creators | Secure first launch or beta creators. | 📋 Not Started | Needed for a credible launch marketplace.
Create creator onboarding docs | How-to for setup, posting, pricing, tier themes, and policy. | 📋 Not Started | Helpful for beta and early launch.
Define beta member invite list | Choose initial users to test flows. | 📋 Not Started | Needed for private beta.
Build waitlist / lead capture | Collect early interest before public release. | 📋 Not Started | Useful for launch momentum.
Create social launch content plan | Posts, teasers, launch announcements. | 📋 Not Started | Needed before public launch.
Define referral / affiliate plan | Lightweight growth loop for early users. | 📋 Not Started | Can be simple but useful.
Build Pumdoki Discord Server | Marketing tool to build audience, recruit our first creators, and create a community. | 🔄 In Progress | Needed before public launch.
🧪 PHASE 12 — QA, Beta & Launch
Build internal QA checklist | Turn roadmap into a structured test list. | 🔄 In Progress | Repository checks and real-stack browser coverage are established, including merged routing, auth, Settings, and creator-application flows. The broader product, beta, payment, moderation, and launch QA checklist remains incomplete.
Plan private beta | Define who tests, what gets tested, how feedback is captured. | 📋 Not Started | Recommended before public launch.
Run end-to-end flow testing | Test signup → content → subscription → gating → payout → admin. | 📋 Not Started | Needed after core build is ready.
Run security review | Auth, media access, role checks, secrets, signed URLs, abuse risks. | 📋 Not Started | Needed before public launch.
Run payment flow testing | CCBill → Epoch cascade, subscription lifecycle, renewal, cancel, chargebacks. | 📋 Not Started | CCBill site prep underway. Testing awaits implemented processor flows; cascade only if confirmed.
Prepare soft-launch go/no-go checklist | Define criteria for a limited launch. | 📋 Not Started | Useful before broad release.
Prepare public launch checklist | Confirm readiness: product, legal, payments, support, marketing. | 📋 Not Started | Final pre-launch checkpoint.
Define post-launch bug triage process | Severity rules and response rhythm for launch issues. | 📋 Not Started | Needed once public users arrive.
🧭 PHASE 13 — June 2026 Scope & Architecture Decisions
Implement tipping / Send Love | Allow members to tip creators with idempotent payment evidence and creator pending earnings. Payment method remains unresolved. | 📋 Not Started | Moved from backlog into MVP launch scope.
Implement PPV purchases | Allow members to unlock individual creator content with durable entitlement records. Payment method remains unresolved. | 📋 Not Started | Moved from backlog into MVP launch scope.
Implement real-time WebSocket messaging | Authenticated direct messages with persistence, reconnect, read states, presence, rate limits, block, and report. | 📋 Not Started | Basic real-time DMs are launch scope; advanced group/chat features remain post-MVP.
Complete Store for launch | Connect Store tabs, search, purchase, history, favorites, liked content, filters, and responsive four-card desktop presentation to real data. | 🔄 In Progress | UI prototype exists; backend and payment integration remain.
Complete Connect for launch | Implement service setup, schedules, time zones, payment rules, confirmations, cancellations, disputes and reviews. | 🔄 In Progress | UI prototype exists; full booking lifecycle remains.
Complete Oasis / Drimy for launch | Create server-authoritative Drimy ownership, XP, Orbs, tasks, evolution, inventory, achievements, and daily resets. | 🔄 In Progress | Moved from post-MVP into launch scope; current page is client-only mock logic.
Build Oasis collectibles and cosmetics | Create collectible backgrounds, skins, frames, badges, equipped states, fixed-price store items, and reward inventory. | 📋 Not Started | Primary objective is daily retention. Paid randomized rewards require separate review.
Implement explicit-content preference | Add hide/show 18+ content choice to onboarding, Settings, feed, search, Store, and Connect; default hidden. | 🔄 In Progress | Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. Onboarding and server-side feed/search/Store/Connect enforcement remain pending.
Define international launch allowlist | Enable countries only after payment, payout, identity, adult-content law, privacy, tax, sanctions, and support review. | 📋 Not Started | Prioritize USA and selected Latin American countries; phase EU/EEA carefully.
Support Latin American creator onboarding | Plan Spanish localization, local IDs, tax residency, payout support, time zones, and region-appropriate assistance. | 📋 Not Started | Core creator acquisition requirement.
Select identity verification approach | Compare specialist providers and a tightly controlled manual-beta workflow; design for later provider migration. | 📋 Not Started | Manual review requires encrypted isolated storage, strict access, and audit logs.
Define initial media upload limits | Start with cost-conscious limits and direct R2 uploads; measure beta storage/transcoding cost before raising limits. | 📋 Not Started | Provisional: images 20 MB, video 1 GB/30 min, audio 250 MB, ID files 10 MB.
Select transactional email provider | Evaluate Amazon SES first, verify adult-business support, and implement verification, reset, billing, moderation, and booking mail. | 📋 Not Started | Provider-neutral SMTP/console abstraction and local Mailpit are implemented. Production provider selection, adult-business support, deliverability, TLS, DKIM, SPF, and DMARC remain open.
Choose LLC state and privacy structure | Compare Wyoming and other candidates with an adult-platform attorney and CPA; include registered agent, taxes, and foreign qualification. | 📋 Not Started | No entity filed. A no-income-tax state does not by itself remove taxes or disclosure duties elsewhere.
Decide commission and payout model | Model processor fees, chargebacks, refunds, taxes, platform fee, Founding Creator discount, payout cadence, and minimum. | 📋 Not Started | Do not publish the current 80/20 mock copy until actual processor economics are known.
Define private operations architecture | Build a separately deployed private operations application with API-enforced ADMIN permissions, stronger access controls, sensitive-record permissions, and immutable audit logging. | 🔄 In Progress | A separate apps/admin shell, dormant injected-verifier review seam, and merged non-secret G1–G12 readiness packet exist. The router is unmounted; production authentication, restricted hosting, phishing-resistant hardware-backed assurance, operator provisioning, origin/CSRF controls, trusted-proxy handling, restricted DB grants, immutable audit, and deployment are absent; all gates are NOT EVALUATED.
Adopt TypeScript backend and shared contracts | Keep the current web prototype in JavaScript initially; write new API/database/contracts in TypeScript and migrate frontend gradually. | 🔄 In Progress | TypeScript API/contracts/database foundations now cover auth, protected Settings, creator applications, and the dormant review seam; frontend conversion remains incremental.
Replace prototype contact addresses | Replace unconfigured production-looking emails with .example sample addresses until real domains and mailboxes are operational. | 📋 Not Started | Legal and support UI must not imply nonexistent operations.
Prepare public-member / controlled-creator beta | Allow public member registration when safe while onboarding creators through verification and approval controls. | 🔄 In Progress | Public member registration exists, while creator applications remain PENDING and identity NOT_STARTED. No approval, role promotion, identity/tax/banking intake, deployed reviewer workflow, or creator publishing gate exists; controlled beta readiness remains incomplete.
Confirm CCBill → Epoch cascade | Obtain written technical and commercial confirmation before implementing fallback payment routing. | 📋 Not Started | CCBill Sales replied; site prep underway. Written cascade confirmation and Epoch outreach remain pending.

## Backlog
Feature | Category | Why Later | Priority | Status | Note
Live streaming | Engagement | Delay until MVP stability and core monetization proven. | Medium | 📋 Not Started | Explicitly deferred from MVP.
Advanced chat / real-time messaging | Engagement | Advanced group chat, rich collaboration, and higher-complexity messaging remain later; basic authenticated WebSocket DMs moved to MVP. | Medium | 📋 Not Started | MVP includes real-time direct messages only. Advanced chat remains deferred.
Tipping | Monetization | Moved into the launch MVP by founder decision on June 21, 2026. | Critical | ➡️ Moved to MVP | Tracked in Master Tracker: Implement tipping / Send Love.
Pay-per-view content | Monetization | Moved into the launch MVP by founder decision on June 21, 2026. | Critical | ➡️ Moved to MVP | Tracked in Master Tracker: Implement PPV purchases.
Advanced analytics | Analytics | Add richer creator/member analytics after launch. | Medium | 📋 Not Started | Explicitly deferred from MVP.
Recommendation engine | Discovery | Delay algorithmic rec until enough data exists. | Low | 📋 Not Started | Explicitly deferred from MVP.
Multiple themes (beyond Sakura Kiss & Midnight City) | Design | Ship two strong default themes first, then add premium ones. | Low | 📋 Not Started | Additional premium themes deferred post-MVP.
Heavy gamification (Oasis / Drimys) | Engagement | Moved into the launch MVP by founder decision on June 21, 2026. | Critical | ➡️ Moved to MVP | Oasis/Drimy is now launch scope for daily retention, collectibles, backgrounds, and skins.
Crypto payments (USDT/BTC) | Monetization | Planned but deferred until fiat payments proven. | Medium | 📋 Not Started | Research: self-hosted vs NowPayments/PayRam.
Pumdoki Premium (Nitro-style) | Monetization | Banners, medals, badges for any paying user. | Medium | 📋 Not Started | Similar to Discord Nitro.
Creator verification badges | Trust & Safety | Verified creator program with identity checks. | Medium | 📋 Not Started | Adds trust; defer until creator base grows.
Mobile app (iOS / Android) | Platform | Native mobile after web platform is stable. | High | 📋 Not Started | Web-first; mobile later.
TikTok paid creator promotions | Marketing | Requires budget, live product, and something worth promoting. No point driving traffic before launch. | Medium | 📋 Not Started | Standard influencer marketing strategy. Frame campaigns as 'creator monetization platform' — avoid direct NSFW references to stay within TikTok ad policies. Revisit 1–2 months post-launch once conversion data exists.
Kick platform integration / clipping strategy | Partnerships | Long-term scaling play requiring funding, an established creator base, and platform stability. Not a bootstrapped v1 move. | Low | 📋 Not Started | Kick's permissive content policy makes it a natural partner platform long-term. Could drive creator and member acquisition at scale. Requires meaningful budget and an established Pumdoki audience first. Far-future item.
Live streaming on Creator Dashboard | Design | "Re-enable the 'Live Streaming' feature by setting the conditional boolean to true, restoring both the sidebar navigation link and the main view component." | Low | 📋 Not Started | Reactivate the livestream feature on the creator Dashboard after it's fully implemented on the website

## Notes & Assumptions
📝 Notes & Assumptions
Rule | Detail
1.0 | This workbook is reconciled with the repository, founder decisions, and merged PR #1–#3 baseline through August 16, 2026.
2.0 | ✅ Done = clearly locked in prior planning or confirmed in recent discussions.
3.0 | 🔄 In Progress = explicitly underway or being organized/planned.
4.0 | 📋 Not Started = required for launch but not confirmed as underway.
5.0 | Master Tracker focuses on MVP/launch needs; the Backlog sheet captures post-MVP features.
6.0 | Upload to Google Sheets for online collaboration — add owners and dates there.
7.0 | Suggested next use: filter by Not Started to decide immediate work.
8.0 | Legal/compliance expanded with 8 additional tasks from LoyalFans March 2026 gap analysis.
9.0 | Admin dashboard (Phase 9) expanded — 13 subtasks covering all operator tools needed for an adult content platform.
10.0 | Phase 6 expanded — added: NSFW toggle, Settings, Help/Support, Activity, modal/drawer/chat fixes, creator dashboard.
11.0 | Midnight City is implemented as the second free default theme alongside Sakura Kiss, with browser-local selection.
12.0 | Founding Creator / Member badge program added to Phase 3 — first 500 creators get reduced commission + permanent badge.
🌸 Known Context Captured
• | Brand: pink/sakura aesthetic. Pearl/off-white on soft sakura pink. Soft, dreamy, intimate, polished, premium.
• | Logo: minimal heart + sakura petal + subtle heartbeat icon + rounded sans-serif wordmark.
• | Motto: 'A space for creators, members, and real interaction.'
• | Tiers: Standard Support (Doki 1, 2, 3), Premium Support (Super Doki 1, 2), Ultimate (Doki Legend).
• | Creator themes: Floral (Petal→Bloom→Sakura→Golden Sakura→Eternal Sakura), Ember (Ember→Ignite→Flare→Inferno→Eternal Flame).
• | Infrastructure: AWS for app layer + RDS PostgreSQL for database.
• | Media storage/CDN: Cloudflare R2 (NSFW-safe, free egress, no restrictive AUP on legal adult content).
• | CCBill is the intended primary processor. Sales has replied; merchant/model approval and technical integration remain pending.
• | Epoch is the intended fallback. Outreach and account-specific cascade confirmation remain pending; no routing is implemented.
• | Future payment rail: Crypto (USDT/BTC) — planned post-MVP.
• | Pumdoki Premium: banners, medals, badges — like Discord Nitro, open to any paying user. Post-MVP.
• | NSFW content allowed from day 1. +18 toggle required in settings and feed.
• | Admin operations: separate apps/admin shell; no public /admin. Public ADMIN sessions are insufficient for operations access. The dormant review router stays unmounted until signed operations identity, exact provisioning, phishing-resistant hardware-backed assurance, private-origin/CSRF, trusted-proxy, restricted DB-role, audit, and recovery gates pass.
• | Midnight City: blue city rooftops, static desktop/mobile JPGs. Browser-local Settings selection implemented; account sync pending.
• | Founding Creator/Member badge: first 500 creators = reduced fee + permanent badge. First 500 members = badge + discount.
• | Git branches: Home, Landing, Store, Connect, Chat.
• | Build style: visual/iterative — needs to see UI to know what to change.
• | Privacy concern: Maryland biz records may expose identity linked to NSFW platform.
• | Feed/story: heart story rail + For You/Following tabs confirmed in design.
• | Homepage messaging avoids 'Softer'; should feel for everyone, not creator-first.
• | Company structure: LLC recommended (US adult platforms standard). Epal, Fansly = LLC. OnlyFans = UK Ltd.
• | Legal must be drafted BEFORE first creator is onboarded — not just before public launch.
• | Oasis / Drimys is now launch scope. It targets daily retention through XP, Orbs, evolution, tasks, backgrounds, skins, frames, badges, and collectibles.
🚀 Current Delivery Plan
Plan source | PLAN.md remains the architecture source of truth. PR #1 merged Phase 4 creator-application persistence plus the dormant non-approval review foundation; PR #2 merged routing hardening; PR #3 merged non-secret operations-readiness documentation.
Immediate 1 | PR #1 (e7352c8), PR #2 (1189404), and PR #3 (80efce5) are merged into dev after green reviewed-head CI. The public API still does not mount the creator-review router, and the readiness packet is planning—not live-control evidence.
Immediate 2 | Keep Phase 2 labeled partially complete: staging, backup/restore drills, monitoring/alerts, shared Redis throttling, queue/idempotency architecture, and production email decisions remain open.
Immediate 3 | Before any private-operations activation, implement and evaluate G1–G12: signed operations identity, exact operator provisioning, phishing-resistant hardware-backed assurance, private origin plus mutation CSRF/origin validation, trusted-proxy handling, restricted database roles, audit destination, recovery, and abuse tests.
Immediate 4 | Obtain counsel/CPA guidance and concrete identity-provider, country-allowlist, retention, CCBill/Epoch, tax, payout, and operational-mailbox inputs before irreversible compliance or payment workflows.
Immediate 5 | Keep APPROVED, creator-role promotion, identity files, tax/banking intake, payment/ledger effects, creator publishing, staging deployment, and production activation disabled until their legal, provider, security, and operational gates are concrete.
✅ July 7, 2026 — Confirmed Founder Decisions
• | Phase 3 starts on the local stack while Phase 2 remains explicitly partially complete.
• | First beta uses email/password only; Google OAuth is not beta scope.
• | Phase 3 is decomposed into four slices: core auth backend, email flows, frontend integration, and Settings.
• | Sessions use opaque tokens with 30-day sliding expiry, renewed at most once per day.
• | Acceptance records are append-only with restrictive deletion; future account deletion must follow counsel-approved retention and pseudonymization rules.
• | Slice 3 connects the frontend to live auth APIs, including persistent cookie sessions, verification, password reset, role guards, and logout.
• | Core-auth implementation uses Argon2id and transparently upgrades the development scrypt seed format after a successful login.
• | Email verification, password reset, frontend auth integration, protected Settings, and explicit-content preference persistence are published and CI-verified. OAuth, a production email provider, and Redis-backed throttling remain later work.
✅ July 28, 2026 — Phase 3 Slice 2 Verification
• | Provider-neutral SMTP/console mail, local Mailpit, verification and reset templates, and validated mail environment variables are implemented.
• | Verification and reset tokens are random, hashed at rest, expiring, single-use, and invalidated on reissue; password reset revokes all sessions.
• | Phase 3 Slice 4B publishes the founder-approved core account-security scope: display-name edit, email change/reverification, authenticated password change, and active-session listing/revocation. Notifications wait for Phase 9; billing for payments; export/deletion for counsel-approved retention; theme for design-system work; explicit-content query enforcement for Phase 5 APIs.
✅ June 21, 2026 — Confirmed Founder Decisions
• | Oasis/Drimy must be functional at launch.
• | Store and Connect are launch-critical.
• | Tipping, Send Love, and PPV are MVP launch scope.
• | Live streaming remains post-MVP.
• | CCBill Sales replied and functioning-site preparation is underway. Password protection is permitted. Epoch outreach remains pending.
• | CCBill-to-Epoch cascade behavior is not yet confirmed.
• | Commission, Founding Creator discount, payout cadence, and minimum payout remain undecided.
• | The LLC is not filed. Founder prioritizes privacy and is considering a no-individual-income-tax state.
• | Recommended stack: TypeScript for new API/contracts, gradual frontend conversion, Express, PostgreSQL, and Prisma.
• | Recommended auth: one Pumdoki-owned account/session system with optional OAuth login methods later.
• | Founder decision (2026-08-01): no public /admin route. A separate apps/admin shell and dormant injected-verifier review seam exist, but public ADMIN authorization alone is insufficient; production operations identity, access controls, workflow UI, and deployment remain absent.
• | International launch should use a phased country allowlist rather than enabling every country immediately.
• | Latin American creators are a core audience and require Spanish, local ID, tax, and payout support.
• | Identity verification may start with a tightly controlled manual beta only if security/legal controls exist; design for provider migration.
• | Use cost-conscious initial media limits and direct Cloudflare R2 uploads.
• | Keep performer/consent records simple in the UI while supporting multiple performers in the data model.
• | Creator membership tiers are standardized.
• | Store purchases remain launch scope. Payment method is unresolved.
• | Connect remains launch scope. Payment and service rules need definition.
• | MVP direct messaging uses real WebSockets.
• | Email provider is undecided; evaluate Amazon SES and provider adult-business support.
• | Use .example sample addresses until real operational mailboxes exist.
• | No legal counsel has approved policies yet.
• | Members need a hide/show explicit 18+ content preference; default hidden is recommended.
• | Store target: four noticeable medium YouTube-like thumbnails on common large desktops; scale column count with screen width.
• | Oasis targets daily retention with collectible backgrounds, skins, frames, badges, and related cosmetics.
• | Preserve the current uncommitted frontend work during restructuring.
• | Start with known creators under controlled onboarding while preparing public member registration.
Rows 1–96 retain historical context except scope removed by founder instruction; current operating notes begin below.
📌 Tracker Operating Model — August 21, 2026
Source of truth | PLAN.md Phases 0–14 define the roadmap. Delivery Tracker is the current execution view; HANDOFF.md carries detailed active-slice evidence.
Legacy preservation | The original Master Tracker and Legacy Overview remain visible. No legacy task, note, backlog item, assumption, or expense value was deleted.
Workflow | Not Started, Ready, In Progress, In Review, Blocked, Done, Deferred.
Maturity | Decision Locked means product scope or architecture direction only—never counsel-approved copy or provider approval. Workflow Done never automatically means Production-Ready.
Daily debrief | Append one Daily Log row per meaningful session: goal, change, meaning, exclusions, verification, status, blocker, and next step.
Current focus | Phase 4 Slice 3 is locally implemented at commit 9904334 and authorized for draft-PR review: strict provider-neutral assertion verification, DB-owned operator/grant authorization, and request-integrity seams. It is not mounted, deployed, or operational.
Phase 4 | Creator application and dormant non-approval review foundations are published. The Slice 3 local foundation is in review; legal, live provider/issuer, hosting, session, runtime-role, approval, role-promotion, identity, publishing, and deployment gates remain open. G1–G12 remain NOT EVALUATED.
Expense QC | The visible Year 1 expense total appears inconsistent with visible inputs. It is preserved unchanged and flagged for separate founder review.
Last refreshed | 2026-08-23 by Codex during the authorized Phase 4 Slice 3 local implementation and draft-publication preparation.

## 💸 Expense Tracker
💸 Pumdoki — Expense & Cost Tracker
USD. Estimated costs are historical; see Launch Budget for planning. Actual purchases below were confirmed by the founder September 10, 2026. Transaction dates were not supplied.
Item | Category | Type | Estimated Cost | Actual Cost | Frequency | Status | Notes
🏦 ONE-TIME / SETUP COSTS
CCBill Visa Registration Fee | Payments | One-time | 500 |  | Once | 📋 Not Paid | Required for US merchants to process Visa.
CCBill Mastercard Registration Fee | Payments | One-time | 500 |  | Once | 📋 Not Paid | Required for US merchants to process MC.
Epoch Setup Fee | Payments | One-time | 0 |  | Once | 📋 Not Paid | Typically free — Epoch acts as merchant of record.
USPTO Trademark — 'Pumdoki' | Legal | One-time | 350 |  | Once | 📋 Not Paid | Per class (IC 009, 035, 042). May need 2–3 classes.
Kiban Digital Holdings LLC — Northwest formation | Legal | One-time | 155 | 196 | Once | Paid / filed | Founder confirmed $196 total on September 10. Filed through Northwest; Maryland approval pending. Exact purchase date not supplied. Estimated Cost is the old allowance, not the amount paid.
Policy documents — Suzanne Lawyer (Fiverr) | Legal | One-time | 125 | 1100 | Once | Paid / drafting | Founder confirmed purchase September 10. $1,100 bundle: ToS $150; Privacy/Cookies $150; AUP $100; community rules $100; DMCA $100; NCII/TAKE IT DOWN $100; anti-trafficking $100; complaints/appeals $150; creator/payout terms $150. Offer: 5 revisions, 7 days. Delivery and approval pending. Transaction date and added fees not supplied. No other Fiverr purchases reported.
Registered Agent (annual) | Legal | Annual | 125 |  | Yearly | 📋 Not Paid | Privacy shield for MD biz records. ~$100–150/yr.
Domain Purchase (.com) | Infrastructure | Annual | 15 |  | Yearly | 📋 Not Paid | Primary domain.
Domain Variants (.net, .io) | Infrastructure | Annual | 30 |  | Yearly | 📋 Not Paid | Optional — protect brand.
📆 MONTHLY / RECURRING COSTS
AWS EC2 (t3.small → t3.medium) | Infrastructure | Monthly | 18 |  | Monthly | 📋 Not Paid | Start small ($15–18), scale to medium ($30–35).
AWS RDS PostgreSQL (db.t3.micro) | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | Free tier covers 12 months if new AWS account.
Cloudflare R2 Storage | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | 10GB free. $0.015/GB/mo after. Egress is free.
Cloudflare R2 Operations | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | 10M Class B reads/mo free. Minimal at launch.
SSL/TLS Certificate | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | Free via Cloudflare or Let's Encrypt.
Email Service (SES / Resend) | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | SES: ~$0.10/1K emails. Free tier covers early use.
Error Tracking (Sentry free tier) | Infrastructure | Monthly | 0 |  | Monthly | 📋 Not Paid | Free for 5K events/mo. Enough for launch.
📊 PER-TRANSACTION COSTS (Variable)
CCBill Transaction Fee | Payments | Per-transaction | 0 |  | Per txn | Variable | ~10–14% per transaction. High-risk adult rate.
Epoch Transaction Fee | Payments | Per-transaction | 0 |  | Per txn | Variable | ~10–15% per transaction on cascaded payments.
CCBill Chargeback Fee | Payments | Per-transaction | 0 |  | Per event | Variable | Varies. Budget ~$20–25 per chargeback.
🔮 OPTIONAL / FUTURE COSTS
Crypto Payment Gateway | Payments | Monthly | 0 |  | Monthly | Deferred | Post-MVP. NowPayments ~1%/txn. Self-hosted = free.
Content Watermarking Service | Tools | Monthly | 0 |  | Monthly | Deferred | Evaluate after launch. May build in-house.
DMCA Takedown Service | Legal | Monthly | 0 |  | Monthly | Deferred | Optional. Handle manually at first.
📋 COST SUMMARY
Estimated One-Time Total | 1630
Estimated Annual Total | 170
Estimated Monthly Total (launch) | 18
Estimated Year 1 Total | 2016
Actual paid to date | 1296
Original displayed Year 1 total | 1713
Remaining estimate vs original total | 303
Current budget | See Launch Budget. Old registration, legal, free-tier and processor assumptions are superseded.

## Legacy Overview 2026-08-16
🌸 Pumdoki Master Build Tracker
Google Sheets-compatible workbook built from existing Pumdoki planning context.
📋 MVP Tracker Summary |  |  | 📦 Post-MVP Backlog
Total MVP tasks | 143 |  | Total backlog items | 15
✅ Done | 21 |  | 📋 Not Started | 12
🔄 In Progress | 52
📋 Not Started | 70
% Complete | 0.14685
Status legend |  | Project notes
✅ Done |  | Counts are derived from the Master Tracker through August 16, 2026. Section headers are excluded.
🔄 In Progress |  | • Items without clear evidence of completion defaulted to Not Started.
📋 Not Started |  | • Use the Master Tracker sheet as the working project manager view.
• Upload this .xlsx to Google Sheets for online collaboration.
• Infra locked: AWS (app/DB) + Cloudflare R2 (media).
• Payments locked: CCBill (primary) + Epoch (cascade/fallback).
• Future: Crypto payments (USDT/BTC) planned post-MVP.
Phase 1 and the founder-approved Phase 3 core scope are published and CI-verified. Phase 2 remains partial. PR #1 merged the Phase 4 creator-application and dormant non-approval review foundation, PR #2 merged routing hardening, and PR #3 merged non-secret readiness documentation. The operations router remains unmounted and activation gates G1–G12 are NOT EVALUATED.
Connect Tech LLC
Preservation note
This sheet is the untouched August 16 Overview snapshot retained during the PLAN.md tracker rework.
Use Overview, Phase Roadmap, Delivery Tracker, Review & Blocker Queue, Daily Log, and Decision Register for current project management.
The original Master Tracker remains visible and preserved as the legacy task source.

## Controls
⚙ Pumdoki Tracker Controls & Definitions
Editable dropdown values and concise operating definitions. PLAN.md remains the phase source of truth.
Phase ID | Phase Name | Workflow | Maturity | Priority | Owner | Record Type | Phase State
P00 | Baseline, tracker, and scope control | Not Started | Decision Locked | Critical | Founder | PLAN task | Not Started
P01 | Repository and frontend foundation | Ready | UI Prototype | High | Engineering | PLAN phase gate | Partially Complete
P02 | Backend and database foundation | In Progress | Backend Implemented | Medium | Operations | Supplemental | Foundation Complete
P03 | Authentication, roles, and settings | In Review | Integrated | Low | Counsel | Legacy-mapped task | Complete
P04 | Legal, trust, and creator onboarding | Blocked | Production-Ready |  | Unassigned | Published slice | Blocked
P05 | Media pipeline and content model | Done | N/A |  |  | Decision | Deferred
P06 | Payments, subscriptions, tipping, and PPV | Deferred |  |  |  | Exit criterion
P07 | Core end-to-end vertical slice
P08 | Feed, social actions, Store, and Connect
P09 | Real-time messaging and notifications
P10 | Creator dashboard
P11 | Admin and moderation
P12 | Oasis replacement concept (post-launch)
P13 | Internationalization and accessibility
P14 | QA, security, private beta, and launch
POST | Post-MVP
Operating definitions
Not Started | No implementation is underway. |  | Decision Locked | Product scope or architecture direction is approved; implementation may be absent. This never means counsel-approved copy, provider approval, or production readiness. |  | Source of truth | Delivery Tracker = current execution state; PLAN.md = scope/dependency architecture; HANDOFF.md = active technical evidence.
Ready | Dependencies and owner are clear; implementation can start. |  | UI Prototype | A visual/client prototype exists without authoritative backend behavior. |  | Daily updates | Append one Daily Log row per meaningful work session; never rewrite earlier rows.
In Progress | Work is actively being implemented or verified locally. |  | Backend Implemented | Backend or infrastructure foundation exists but may not be integrated or deployed. |  | Review rule | Open PR or review artifact moves work to In Review; green CI alone does not mark it Done.
In Review | A review artifact exists and awaits review, CI, or approval. |  | Integrated | The defined slice is connected and regression-tested in the product/repository. |  | Done rule | Done requires accepted evidence for the defined scope, not a production claim.
Blocked | Progress requires an external decision, dependency, or authority. |  | Production-Ready | Deployment, operations, security, legal, and recovery gates are verified. |  | Legacy preservation | The original Master Tracker and Legacy Overview remain visible and unchanged as historical source snapshots.
Done | The defined scope was accepted and verified; this does not automatically mean production-ready. |  | N/A | Maturity does not apply to this management/reference row. |  | Expense QC | Historical Year 1 arithmetic corrected to $2,366 on September 6, 2026; old $1,713 retained. Use Launch Budget for current planning.
Deferred | Explicitly outside the current MVP sequence.

## Phase Roadmap
🗺 Pumdoki Phase Roadmap — PLAN.md Phases 0–14
Record progress includes preserved legacy, PLAN, gate, and supplemental records. It is a navigation aid—not phase completion; Phase State is the canonical evidence-based PLAN judgment.
Phase ID | PLAN Phase | Phase State | Maturity | Records Done | Execution Records | Record Progress | In Progress | In Review | Blocked | Not Started | Current Focus | Next Exit Gate | Exit Criteria Summary | Evidence | Updated
P00 | Baseline, tracker, and scope control | Partially Complete | Integrated | 6 | 6 | 100% | 0 | 0 | 0 | 0 | Maintain the PLAN-aligned execution tracker, decision register, review queue, and daily debrief history. | Assign and maintain owners and next-check dates for remaining active decisions; preserve legacy records. | Clean baseline; tracker reflects reality; MVP approved; open decisions have an owner and date. | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00
P01 | Repository and frontend foundation | Complete | Integrated | 4 | 8 | 50% | 4 | 0 | 0 | 0 | Maintain routing, shared shell, fixtures, CI, error states, and code splitting. | No active gate; preserve regression coverage as product phases integrate real data. | Workspace builds; routes and browser navigation work; CI validates lint, tests, builds, and E2E. | https://github.com/QK-Connoisseur/PDoki/pull/2 | 2026-08-21 16:00
P02 | Backend and database foundation | Partially Complete | Backend Implemented | 4 | 16 | 25% | 7 | 0 | 0 | 5 | PR #13 published the application-owned PostgreSQL worker foundation and fixed non-secret canary; no product flow uses it. | Keep Phase 2 partial: staging, restore/backups, monitoring, Redis/shared throttling, general idempotency, and deployment remain open. | HTTPS staging; repeatable migrations; backup restoration; monitoring; durable worker foundation reviewed. | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00
P03 | Authentication, roles, and settings | Complete | Integrated | 6 | 8 | 75% | 2 | 0 | 0 | 0 | Maintain the founder-approved reduced core auth/account-security scope. | Later Settings domains move only with their dependency phases. | Persistent auth; protected routes; API permissions; explicit-content preference persists safely. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#7-phase-3--authentication-roles-and-settings | 2026-08-21 16:00
P04 | Legal, trust, and creator onboarding | Partially Complete | Backend Implemented | 5 | 35 | 14.29% | 18 | 0 | 0 | 12 | Slices 1–4 published; operations dormant. Maryland approval pending. Initial CCBill reply retained; proposed follow-up cancelled. Founder/provider work now accompanies each functional code slice. | Resolve business/legal/provider prerequisites in sequence. G1–G12 apply to operations activation, not all synthetic local product work. | Counsel-approved policies; secure identity/evidence; publishing blocked until approval; reports are auditable. | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00
P05 | Media pipeline and content model | Partially Complete | Backend Implemented | 1 | 10 | 10% | 4 | 2 | 0 | 3 | Safe photo/video flow now uses private R2 storage. Cloud upload/read, private drafts, publish/feed, ranges, restart persistence and removal are verified. Test accounts only. Hosted review deployment and production media controls remain open. | Founder reviews the working local R2 upload/publish flow for this slice. No new signup, paperwork or payment task. Real identity, adult uploads and payments remain disabled. Full P05 exit, deployment and processor approval remain open. | Approved creators publish; unauthorized users cannot access originals; takedowns invalidate delivery. | HANDOFF.md | 2026-09-09 16:00
P06 | Payments, subscriptions, tipping, and PPV | Partially Complete | UI Prototype | 0 | 16 | 0% | 3 | 0 | 0 | 13 | Provider/site preparation is in progress: CCBill Sales replied, safe-content/R2 milestone is verified and policy drafting is commissioned. Payment backend, webhooks and paid entitlements have not started. | Continue functioning-site slices; password protection is permitted for later review. Founder reviews the current local flow. Return to CCBill when review-ready; define the supported payment method before integration. | For paid beta flows: trusted payment events, entitlements, earnings, refunds and chargebacks reconcile. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md | 2026-09-10 16:00
P07 | Core end-to-end vertical slice | Blocked | N/A | 0 | 1 | 0% | 0 | 0 | 1 | 0 | Core journey still needs creator, content/access and operations controls. Apply payment dependencies to the chosen beta method. | Continue safe test flows. Define the beta payment model with its slice; any paid flow requires processor confirmation, entitlements, auditable earnings and reconciliation. | Agreed beta journey passes automated tests without manual DB edits. Paid flows satisfy payment, access and audit controls. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#11-phase-7--core-end-to-end-vertical-slice | 2026-09-09 16:00
P08 | Feed, social actions, Store, and Connect | Partially Complete | UI Prototype | 4 | 10 | 40% | 6 | 0 | 0 | 0 | Feed, Store and Connect remain launch scope (online/price/language discovery). Your Activity /activity UI is an explicit example-data preview; real member history remains pending. | Integrate content/access, service/order and beta payment rules. Connect Your Activity to authenticated P05/P06/P07 data. | Feed actions persist; Store and Your Activity use real account data; creator discovery filters work. Service/order/payment rules separately defined. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#12-phase-8--feed-social-actions-store-and-connect | 2026-09-10 16:00
P09 | Real-time messaging and notifications | Partially Complete | UI Prototype | 1 | 4 | 25% | 2 | 0 | 0 | 1 | Real-time direct chat remains required at launch. Prototype bell/activities do not establish persisted product notifications. | Approve conversation/message persistence and WebSocket authorization design. | Messages survive reconnect; conversation access is authorized; notifications persist and mark read. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#13-phase-9--real-time-messaging-and-notifications | 2026-09-06 16:00
P10 | Creator dashboard | Partially Complete | UI Prototype | 0 | 1 | 0% | 1 | 0 | 0 | 0 | Large UI prototype exists; backend data, actions, and financial reconciliation are absent. | Connect dashboard modules only after their source domains are implemented. | Figures use real data; launch actions work; financial totals reconcile. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#14-phase-10--creator-dashboard | 2026-08-21 16:00
P11 | Admin and moderation | Blocked | Backend Implemented | 0 | 14 | 0% | 2 | 0 | 0 | 12 | Dormant operations source remains parked. The next planned P05 test-content flow pairs storage decisions with implementation. No deployment, live payment or identity activation is implied. | Evaluate provider, restricted hosting, MFA/recovery, session, permission, audit and deployment controls when activating real operations. | Founder operates without DB access; reports/payments/verification are manageable; sensitive access is audited. | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00
P12 | Oasis replacement concept (post-launch) | Deferred | UI Prototype | 0 | 2 | 0% | 0 | 0 | 0 | 0 | Old Oasis/Drimy game CANCELLED on September 6, 2026. Name may be reused for day/friend streaks and playful adult language learning. | No launch gate. Define the replacement after launch; opt-in roasting and language concept remain unimplemented. | Old game exit criteria superseded. Future concept requires its own approved scope. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md | 2026-09-06 16:00
P13 | Internationalization and accessibility | Partially Complete | UI Prototype | 0 | 2 | 0% | 1 | 0 | 0 | 1 | Scattered responsive/accessibility work exists; bilingual core flows and a formal audit remain open. | Extract UI copy and scope English/Spanish plus keyboard, focus, contrast, screen-reader, and reduced-motion work. | Core flows work in English/Spanish; accessibility audit has no critical failures. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#17-phase-13--internationalization-and-accessibility | 2026-08-21 16:00
P14 | QA, security, private beta, and launch | Partially Complete | Integrated | 1 | 22 | 4.545% | 3 | 0 | 0 | 18 | CI/E2E foundations and the deterministic promotion clock fix are published; product E2E, security drills, beta, and launch gates remain open. | Verify applicable creator, content, security, recovery and support controls for beta. Paid flows also need processor and payment controls. | Restore/security/processor/content/support drills pass; launch gates are satisfied; no critical findings. | https://github.com/QK-Connoisseur/PDoki/actions/runs/32535922437 | 2026-09-09 16:00
POST | Post-MVP | Deferred | N/A | 0 | 1 | 0% | 0 | 0 | 0 | 1 | Live streaming, advanced recommendations, native apps, crypto, extra themes, and advanced group chat remain deferred. | Revisit only after launch stability and core monetization evidence. | Not an MVP exit gate. | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#19-post-mvp | 2026-08-21 16:00

## Delivery Tracker
🌸 Pumdoki Delivery Tracker — PLAN.md Aligned
Canonical execution view. The original Master Tracker remains preserved; use filters for phase, workflow, owner, and review state.
Work ID | Phase ID | PLAN Phase | Related Phase(s) | Record Type | Workstream | Work Item | Workflow | Maturity | Priority | Owner | Waiting On / Reviewer | Next Action | Next Check | Evidence | Updated | Scope / Description | Notes / History | Legacy Source
LEG-MT-005 | P00 | Baseline, tracker, and scope control |  | Legacy-mapped task | Baseline, tracker, and scope control | Define core value proposition | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Lock the core promise for creators, members, and interaction. | Positioning: 'A space for creators, members, and real interaction.' | Preserved Master Tracker row 5; legacy status: ✅ Done
LEG-MT-006 | P00 | Baseline, tracker, and scope control |  | Legacy-mapped task | Baseline, tracker, and scope control | Lock MVP scope | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Subscriptions-first, NSFW at launch. Confirm what is excluded from v1. | MVP scope set. | Preserved Master Tracker row 6; legacy status: ✅ Done
LEG-MT-007 | P00 | Baseline, tracker, and scope control |  | Legacy-mapped task | Baseline, tracker, and scope control | Document post-MVP delays | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Keep live streaming, advanced chat, tipping, PPV, analytics, rec engine, extra themes, gamification out of MVP. | MVP vs later items distinguished. | Preserved Master Tracker row 7; legacy status: ✅ Done
LEG-MT-008 | P00 | Baseline, tracker, and scope control |  | Legacy-mapped task | Baseline, tracker, and scope control | Convert roadmap into phase plan | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  | https://github.com/QK-Connoisseur/PDoki/pull/1 | 2026-08-16 16:00 | Break work into design, build, test, beta, and launch phases. | Dependency-ordered PLAN.md is established and current through the merged PR #1–#3 baseline; tracker reconciliation is now ongoing maintenance. | Preserved Master Tracker row 8; legacy status: ✅ Done
LEG-MT-009 | P14 | QA, security, private beta, and launch | P00 | Legacy-mapped task | Quality, beta & launch readiness | Set launch KPIs | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Define targets: creators onboarded, paid members, conversion, retention, bug rate. | Needed before beta/public launch. | Preserved Master Tracker row 9; legacy status: 📋 Not Started
LEG-MT-011 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Terms of Service | In Progress | N/A | Critical | Founder |  | Close the remaining gap: Must exist before launch. |  |  | 2026-08-16 16:00 | Prepare terms governing platform use, NSFW content rules, user responsibilities, dispute resolution. | Suzanne Lawyer hired on Fiverr for the $1,100 policy-document bundle. Draft delivery and review pending. | Preserved Master Tracker row 11; legacy status: 🔄 In Progress
LEG-MT-012 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Privacy Policy | In Progress | N/A | Medium | Founder |  | Close the remaining gap: Privacy layers discussed; formal draft needed. |  |  | 2026-08-16 16:00 | Data collection, cookies, third-party sharing, CCPA/GDPR rights, data retention. | Privacy layers discussed; formal draft needed. | Preserved Master Tracker row 12; legacy status: 🔄 In Progress
LEG-MT-013 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Community / Platform Rules | In Progress | Decision Locked | High | Founder |  | Close the remaining gap: Required for moderation consistency. |  |  | 2026-08-16 16:00 | State permitted and prohibited activity clearly for creators and members. | Required for moderation consistency. | Preserved Master Tracker row 13; legacy status: 🔄 In Progress
LEG-MT-014 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Acceptable Use Policy | In Progress | N/A | High | Founder | Counsel / founder decision | Close the remaining gap: Separates from ToS for clarity and enforcement. |  |  | 2026-08-16 16:00 | No minors, no non-consensual content, no illegal material, no harassment. | Separates from ToS for clarity and enforcement. | Preserved Master Tracker row 14; legacy status: 🔄 In Progress
LEG-MT-015 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Create DMCA Policy & Takedown Process | In Progress | Decision Locked | High | Founder |  | Close the remaining gap: Required for content platforms. |  |  | 2026-08-16 16:00 | Copyright reporting form, designated agent, response procedures (17 USC §512). | Required for content platforms. | Preserved Master Tracker row 15; legacy status: 🔄 In Progress
LEG-MT-016 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Implement 18 USC §2257 Recordkeeping | In Progress | N/A | Critical | Engineering |  | Close the remaining gap: Federal requirement for adult content platforms. |  |  | 2026-08-16 16:00 | Maintain age verification records for performers in sexually explicit content. Display §2257 compliance statement. | Federal requirement for adult content platforms. | Preserved Master Tracker row 16; legacy status: 🔄 In Progress
LEG-MT-017 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Cookie Policy & Consent Banner | In Progress | N/A | High | Founder |  | Close the remaining gap: Required for EU visitors; best practice globally. |  |  | 2026-08-16 16:00 | Disclose cookie usage, purposes, opt-out. Implement consent UI (required for GDPR/ePrivacy). | Required for EU visitors; best practice globally. | Preserved Master Tracker row 17; legacy status: 🔄 In Progress
LEG-MT-018 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Implement GDPR Compliance | In Progress | Decision Locked | High | Engineering | Founder + provider response | Close the remaining gap: Required if serving EU users. |  |  | 2026-08-16 16:00 | Right to access, deletion, data portability, consent management, DPA with processors. | Required if serving EU users. | Preserved Master Tracker row 18; legacy status: 🔄 In Progress
LEG-MT-019 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Implement CCPA/CPRA Compliance | In Progress | N/A | High | Engineering |  | Close the remaining gap: Required if serving California users. |  |  | 2026-08-16 16:00 | 'Do Not Sell' opt-out, privacy notice for CA residents, data deletion requests. | Required if serving California users. | Preserved Master Tracker row 19; legacy status: 🔄 In Progress
LEG-MT-020 | P04 | Legal, trust, and creator onboarding | P06 | Legacy-mapped task | Legal & compliance | Prepare Payment Provider Compliance Package | In Progress | N/A | High | Engineering | Founder + provider response | Continue functioning-site and policy preparation alongside the current product slice. Assemble account-specific evidence for later CCBill review. |  | docs/product/initial-ccbill-inquiry.md | 2026-09-10 16:00 | Document policies/controls required by CCBill and Epoch for merchant onboarding. | CCBill Sales replied: a functioning online site is required; password protection is allowed. Site preparation is underway, safe-content/R2 milestone is verified and policy drafting is commissioned. Merchant approval, model eligibility, fees and payouts remain unresolved. | Master Tracker row 20; provider preparation reconciled September 10, 2026.
LEG-MT-021 | P04 | Legal, trust, and creator onboarding | P06 | Legacy-mapped task | Creator onboarding & trust | Draft Creator Agreement / Payout Terms | Not Started | N/A | Critical | Founder | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Creator obligations: content ownership, tax (W-9/W-8BEN), payout terms, prohibited content. | Needed before creator onboarding. | Preserved Master Tracker row 21; legacy status: 📋 Not Started
LEG-MT-022 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Implement Visa/Mastercard BRAM Compliance | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Meet Brand Risk and Acquirer Monitoring requirements for adult merchants. | Card network requirement for adult sites. | Preserved Master Tracker row 22; legacy status: 📋 Not Started
LEG-MT-023 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Finalize Trademark Filing Plan | In Progress | N/A | Medium | Founder |  | Close the remaining gap: Trademark timing/classes already considered. |  |  | 2026-08-16 16:00 | Decide classes (IC 009, 035, 042), timing and filing sequence for 'Pumdoki'. | Trademark timing/classes already considered. | Preserved Master Tracker row 23; legacy status: 🔄 In Progress
LEG-MT-024 | P04 | Legal, trust, and creator onboarding | P02 | Legacy-mapped task | Legal & compliance | Finalize Domain Management | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Domain strategy already considered. |  |  | 2026-08-16 16:00 | Secure primary domains and variants (.com, .net, etc.). | Domain strategy already considered. | Preserved Master Tracker row 24; legacy status: 🔄 In Progress
LEG-MT-025 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Address MD Business Registration Privacy | In Progress | N/A | High | Founder | Northwest / founder records | Review the approved filing and published address details when Northwest supplies them; actual state approval remains pending. |  |  | 2026-09-08 16:00 | Manage privacy concerns — MD biz records may expose personal identity linked to NSFW platform. | Founder reports Kiban Digital Holdings LLC filed in Maryland through Northwest, awaiting approval. Final published address/privacy details remain unverified. State-comparison task is superseded. | Preserved Master Tracker row 25; legacy status: 🔄 In Progress
LEG-MT-026 | P13 | Internationalization and accessibility |  | Legacy-mapped task | Internationalization and accessibility | Implement Accessibility Basics (ADA/WCAG) | Not Started | N/A | High | Engineering | Counsel / founder decision | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Alt text, keyboard navigation, contrast ratios, screen reader compatibility. | Best practice; reduces legal risk. | Preserved Master Tracker row 26; legacy status: 📋 Not Started
LEG-MT-027 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Anti-Human Trafficking Policy | In Progress | N/A | High | Founder | Founder + provider response | Await the commissioned draft, then review and approve it before publication or operational reliance. |  | Expense Tracker row 11; founder-confirmed Suzanne Lawyer $1,100 document bundle, including anti-trafficking policy. | 2026-09-10 16:00 | Prohibit trafficking, exploitation, coercive content. Include reporting mechanisms and creator guidance. | Drafting commissioned within the purchased policy bundle. Delivery and substantive approval remain pending. | Master Tracker row 27; purchased drafting recorded September 10, 2026.
LEG-MT-028 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Non-Consensual Content Policy | Not Started | N/A | High | Founder | Founder + provider response | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Standalone policy prohibiting NCII. Define removal process, reporting path, and creator obligations. | Must be its own doc for payment processor and Visa/MC BRAM review. | Preserved Master Tracker row 28; legacy status: 📋 Not Started
LEG-MT-029 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Implement US Take It Down Act Compliance | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Written policy + removal workflow for non-consensual intimate images. Must action valid removal within 48 hours. | Federal law signed 2025. Non-compliance is a federal offense. | Preserved Master Tracker row 29; legacy status: 📋 Not Started
LEG-MT-030 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Law Enforcement Request Policy | Not Started | N/A | High | Founder | Counsel / founder decision | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Define process for handling government and LEA data requests — disclosure, legal basis, user notification. | Commonly reviewed during CCBill/Epoch onboarding. | Preserved Master Tracker row 30; legacy status: 📋 Not Started
LEG-MT-031 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Appeals Policy | Not Started | N/A | Critical | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Documented process for creators and members to appeal content removals, account suspensions, or payment holds. | Needed before creator onboarding begins. | Preserved Master Tracker row 31; legacy status: 📋 Not Started
LEG-MT-032 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Complaint Policy | Not Started | N/A | High | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Formal intake process for user complaints beyond DMCA — billing disputes, harassment, platform conduct. | Best practice globally; supports EU DSA/P2B compliance. | Preserved Master Tracker row 32; legacy status: 📋 Not Started
LEG-MT-033 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Anti-Spam Policy | Not Started | N/A | High | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Rules governing creator messaging to members, platform notifications, and marketing emails. | Needed before the email/notification system goes live. | Preserved Master Tracker row 33; legacy status: 📋 Not Started
LEG-MT-034 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Draft Platform-to-Business (P2B) Terms | Not Started | N/A | Medium | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | EU P2B regulation disclosure for creators — ranking criteria, access termination conditions, dispute options. | Conditional on EU launch scope. Low effort to draft. | Preserved Master Tracker row 34; legacy status: 📋 Not Started
LEG-MT-036 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Finalize brand aesthetic & color system | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Confirm pink / sakura visual direction and supporting palette. | Brand direction established. | Preserved Master Tracker row 36; legacy status: ✅ Done
LEG-MT-037 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Finalize logo / wordmark | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Direction exists; final asset lock not confirmed. |  |  | 2026-08-16 16:00 | Lock minimal premium wordmark. Symbol: heart + sakura petal + heartbeat + rounded sans-serif. | Direction exists; final asset lock not confirmed. | Preserved Master Tracker row 37; legacy status: 🔄 In Progress
LEG-MT-038 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Finalize homepage messaging | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Draft messaging exists; final copy not confirmed. |  |  | 2026-08-16 16:00 | Polish hero copy, value prop, marketing text. Avoid 'Softer'; feel inclusive, not creator-first. | Draft messaging exists; final copy not confirmed. | Preserved Master Tracker row 38; legacy status: 🔄 In Progress
LEG-MT-039 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Define creator theme ladders | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Floral: Petal→Bloom→Sakura→Golden Sakura→Eternal Sakura. Ember: Ember→Ignite→Flare→Inferno→Eternal Flame. | Theme ladder concepts defined. | Preserved Master Tracker row 39; legacy status: ✅ Done
LEG-MT-040 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Build reusable design system | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Implied by active UI/front-end development. |  |  | 2026-08-16 16:00 | Buttons, cards, tabs, modals, badges, pricing modules, feed cards, locked-content previews. | Implied by active UI/front-end development. | Preserved Master Tracker row 40; legacy status: 🔄 In Progress
LEG-MT-041 | P13 | Internationalization and accessibility | P01 | Legacy-mapped task | Internationalization and accessibility | Finalize responsive / mobile layouts | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Responsive work remains active. |  |  | 2026-08-16 16:00 | Ensure primary flows work cleanly on mobile and desktop. | Responsive work remains active. A session-aware branded 404, route-level code splitting, and an in-flow dismissible verification reminder are merged and CI-covered on desktop/mobile paths. | Preserved Master Tracker row 41; legacy status: 🔄 In Progress
LEG-MT-042 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Implement Midnight City theme | Done | Integrated | Medium | Engineering |  | Browser-local static theme scope is complete. Account-synced preferences remain separate future work. |  | 0f01961 (#19); apps/web/src/appearance/memberThemeContext.js; MemberThemeProvider.test.jsx; staticBackgroundAssets.test.js; README.md | 2026-09-10 16:00 | Second free theme alongside Sakura Kiss. Blue city rooftops with static desktop/mobile JPG backgrounds. Settings Appearance chooser stores the preference in this browser. | Published implementation; switching and saved preference restoration are tested. Static asset tests cover desktop/mobile JPGs and absence of background video. Internal DARK_KNIGHT key is retained for stored-preference compatibility. | Master Tracker row 42; theme completion reconciled September 10, 2026.
LEG-MT-043 | P06 | Payments, subscriptions, tipping, and PPV | P10, P11 | Legacy-mapped task | Payments & entitlements | Design Founding Creator / Member badge program | Not Started | N/A | Medium | Engineering |  | Define founder badge and a fee that recovers attributable costs without profit on founding creator sales. Duration, covered costs and no-loss economics need validation. |  |  | 2026-09-06 16:00 | Define badge visuals, eligibility window (first N users or date window), locked-in fee reduction for Founding Creators, badge display on profiles and posts. | Founder answers reviewed September 6, 2026: processing-fees-only superseded. Two contacts may recruit 50–100 prospects, not commitments. Longer target ~500; Plus/top 100 rewards remain provisional. | Preserved Master Tracker row 43; legacy status: 📋 Not Started
LEG-MT-045 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Define AWS architecture | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | EC2/ECS for app, RDS PostgreSQL for DB, Cloudflare R2 for media storage/CDN. | AWS (app/DB) + Cloudflare R2 (media) confirmed. | Preserved Master Tracker row 45; legacy status: ✅ Done
LEG-MT-046 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Set up Cloudflare R2 media storage | In Progress | Integrated | Medium | Engineering |  | Broader storage scope remains: signed delivery, CDN caching, retention/garbage collection and recovery/production hardening. |  | HANDOFF.md lines 120–151; docs/architecture/phase5-local-content-flow.md; apps/api/src/content/r2.ts; 86 targeted tests and both R2 browser checks passed. | 2026-09-10 16:00 | Private safe-sample R2 bucket and API integration verified. Signed delivery, CDN caching and production storage lifecycle/recovery remain pending. | R2 activated ($0 due), private review bucket created, Public Access Disabled. Safe PNG/MP4 uploads, authenticated API reads, restart persistence, removal and browser checks passed. Adult-business acceptance unconfirmed; not production-ready. | Master Tracker row 46; safe-sample R2 milestone reconciled September 10, 2026.
LEG-MT-047 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Define RDS PostgreSQL schema | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Local PostgreSQL/Prisma includes User, Session, append-only AcceptanceRecord, VerificationToken, UserPreference, CreatorApplication, creator-policy acceptance, and constrained successful-transition review evidence. |  |  | 2026-09-09 16:00 | Model users, creators, posts, subscriptions, plans, transactions and moderation as needed. | Local PostgreSQL/Prisma includes User, Session, append-only AcceptanceRecord, VerificationToken, UserPreference, CreatorApplication, creator-policy acceptance, and constrained successful-transition review evidence. Remaining product domains and production RDS deployment are pending. | Preserved Master Tracker row 47; legacy status: 🔄 In Progress
LEG-MT-048 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Set up local / staging / prod environments | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Local validated environments plus Docker PostgreSQL/Mailpit exist. |  | https://github.com/QK-Connoisseur/PDoki/pull/3 | 2026-08-16 16:00 | Separate environments, secrets handling, .env management. | Local validated environments plus Docker PostgreSQL/Mailpit exist. PR #3 adds non-secret staging/configuration/verification templates only; staging and production infrastructure, credentials, private origin, and live verification remain pending. | Preserved Master Tracker row 48; legacy status: 🔄 In Progress
LEG-MT-049 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Define API structure | In Progress | Backend Implemented | High | Engineering |  | Close the remaining gap: Implemented /api/v1 health/readiness, auth/email, /me, protected Settings/session, and member creator-application flows. |  |  | 2026-08-16 16:00 | Map endpoints: auth, content, subscriptions, payments, moderation, admin, notifications. | Implemented /api/v1 health/readiness, auth/email, /me, protected Settings/session, and member creator-application flows. The creator-review router remains deliberately unmounted and requires an operations verifier; later product domains remain pending. | Preserved Master Tracker row 49; legacy status: 🔄 In Progress
LEG-MT-050 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Implement logging & monitoring | In Progress | Backend Implemented | Medium | Engineering |  | Close the remaining gap: Structured Pino request logging, request IDs, and secret-header redaction are implemented. |  | https://github.com/QK-Connoisseur/PDoki/pull/3 | 2026-08-16 16:00 | Error tracking, structured logs, operational visibility (CloudWatch, Sentry). | Structured Pino request logging, request IDs, and secret-header redaction are implemented. PR #3 adds a provider scorecard/runbook only; monitoring integration, alerts, retention decisions, and live evidence remain pending. | Preserved Master Tracker row 50; legacy status: 🔄 In Progress
LEG-MT-051 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Implement backups & recovery plan | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Automated RDS snapshots, R2 versioning, disaster recovery. | Required for production readiness. | Preserved Master Tracker row 51; legacy status: 📋 Not Started
LEG-MT-052 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Add rate limiting & abuse protection | In Progress | Backend Implemented | Medium | Engineering |  | Close the remaining gap: Global per-IP limits plus bounded in-memory login and email-request throttles are implemented. |  |  | 2026-08-16 16:00 | Anti-scraping, anti-spam, brute-force protection, credential abuse. | Global per-IP limits plus bounded in-memory login and email-request throttles are implemented. Redis-backed multi-instance protection remains pending. | Preserved Master Tracker row 52; legacy status: 🔄 In Progress
LEG-MT-053 | P02 | Backend and database foundation | P01 | Legacy-mapped task | Backend and database foundation | Set up CI/CD pipeline | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: CI runs formatting, lint, web/API tests and builds, migrations/seed, private-admin build, and real-stack Playwright with read-only token permissions and bounded timeouts. |  | https://github.com/QK-Connoisseur/PDoki/pull/1 | 2026-08-16 16:00 | Automate testing and deployment from Git branches to staging/production. | CI runs formatting, lint, web/API tests and builds, migrations/seed, private-admin build, and real-stack Playwright with read-only token permissions and bounded timeouts. PR #1–#3 passed reviewed-head CI; deployment automation remains pending. | Preserved Master Tracker row 53; legacy status: 🔄 In Progress
LEG-MT-054 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Configure SSL/TLS & domain DNS | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | HTTPS everywhere, DNS records, certificate management. | Required for production. | Preserved Master Tracker row 54; legacy status: 📋 Not Started
LEG-MT-056 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Implement account creation & login/logout | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Create working auth flows, not just screens. | Slice 3 connects registration, login, logout, and authenticated route restoration to the live API. | Preserved Master Tracker row 56; legacy status: ✅ Done
LEG-MT-057 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Implement creator/member/admin roles | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Role-based permissions and access boundaries. | MEMBER/CREATOR route gates and backend role checks are implemented. The public web app has no /admin route; an ADMIN public session is not operational authentication and cannot activate the dormant review router. | Preserved Master Tracker row 57; legacy status: ✅ Done
LEG-MT-058 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Implement session management | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Signed-in state, token/session renewal, logout behavior. | HttpOnly-cookie sessions restore through /me, renew on a bounded sliding window, support logout/logout-all, and can now be listed and individually revoked from protected Settings. Sensitive account changes revoke other sessions. | Preserved Master Tracker row 58; legacy status: ✅ Done
LEG-MT-059 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Creator onboarding & trust | Build onboarding flows | In Progress | Decision Locked | High | Engineering | Founder + counsel/provider | Close the remaining gap: A verified MEMBER can submit one persisted creator application; it remains PENDING with identity NOT_STARTED and no role promotion or Dashboard access. |  |  | 2026-08-16 16:00 | First-run setup for creators (incl. theme selection: Floral/Ember) and members. | A verified MEMBER can submit one persisted creator application; it remains PENDING with identity NOT_STARTED and no role promotion or Dashboard access. Member first-run setup, theme choice, identity/tax/banking intake, and operational approval remain pending. | Preserved Master Tracker row 59; legacy status: 🔄 In Progress
LEG-MT-060 | P04 | Legal, trust, and creator onboarding | P03 | Legacy-mapped task | Creator onboarding & trust | Add 18+ entry gate & age verification | In Progress | N/A | High | Engineering |  | Close the remaining gap: Registration records append-only age attestation and versioned Terms/Privacy acceptance; verified email gates creator-application submission. |  |  | 2026-08-16 16:00 | Consent gating and age/compliance checks at platform entry. | Registration records append-only age attestation and versioned Terms/Privacy acceptance; verified email gates creator-application submission. Entry-gate UI and actual identity/age verification remain pending. | Preserved Master Tracker row 60; legacy status: 🔄 In Progress
LEG-MT-061 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Implement email verification | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Require email confirmation for new accounts. | Slice 3 provides verification screens and Mailpit-backed confirmation. Slice 4B adds authenticated email change, invalidates stale links, requires reverification, and preserves only the current session. | Preserved Master Tracker row 61; legacy status: ✅ Done
LEG-MT-062 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Implement password reset flow | Done | Decision Locked | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Secure forgot-password and recovery process. | Slice 3 provides reset request/confirmation and global revocation. Slice 4B adds current-password-confirmed password change, reset-token invalidation, and other-session revocation. | Preserved Master Tracker row 62; legacy status: ✅ Done
LEG-MT-064 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Build homepage (logged-in feed) | Done | UI Prototype | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Implement the main logged-in home experience with heart story rail and Following/For You tabs. | Feed page designed with heart rail and tab system. Functional layout confirmed. | Preserved Master Tracker row 64; legacy status: ✅ Done
LEG-MT-065 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Build landing page | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Auth/landing split screen complete. |  |  | 2026-08-16 16:00 | Public-facing marketing/conversion page for new visitors. | Auth/landing split screen complete. Raining hearts animation working. +18 checkbox present. | Preserved Master Tracker row 65; legacy status: 🔄 In Progress
LEG-MT-066 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Build creator profile pages | In Progress | UI Prototype | Medium | Engineering |  | Close the remaining gap: Profile page designed. |  |  | 2026-08-16 16:00 | Public creator profiles with plans, content previews, tier display, services tab, highlights. | Profile page designed. Services tab, heart highlights, subscribe button visible. | Preserved Master Tracker row 66; legacy status: 🔄 In Progress
LEG-MT-067 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Build feed / discovery page | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Hybrid discovery feed: For You + Following tabs, heart story rail. | Heart rail + Following/For You hybrid implemented in design. | Preserved Master Tracker row 67; legacy status: ✅ Done
LEG-MT-068 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Build subscription / pricing page | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Part of the active front-end build. |  |  | 2026-08-16 16:00 | Tier display: Standard (Doki 1–3), Premium (Super Doki 1–2), Ultimate (Doki Legend). | Part of the active front-end build. | Preserved Master Tracker row 68; legacy status: 🔄 In Progress
LEG-MT-069 | P03 | Authentication, roles, and settings |  | Legacy-mapped task | Authentication, roles, and settings | Build login / signup screens | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Account entry screens for creators and members. | Live validated API login/signup/logout plus forgot/reset/verify flows are published. Registration was redesigned, verification reminders no longer overlay protected content, and deep-link restoration/session-aware recovery are CI-covered. | Preserved Master Tracker row 69; legacy status: ✅ Done
LEG-MT-070 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Implement story rail / For You model | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Translate the interaction/feed architecture into actual UI behavior. | Heart rail + Following/For You hybrid implemented in design. | Preserved Master Tracker row 70; legacy status: ✅ Done
LEG-MT-071 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Implement locked-content previews | In Progress | UI Prototype | Medium | Engineering |  | Close the remaining gap: Locked preview UI exists; backend entitlement and protected media delivery remain. |  |  | 2026-08-16 16:00 | Teasers and premium access states in cards and posts. | Locked preview UI exists; backend entitlement and protected media delivery remain. | Preserved Master Tracker row 71; legacy status: 🔄 In Progress
LEG-MT-072 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Implement membership tier modules | In Progress | UI Prototype | Medium | Engineering |  | Close the remaining gap: Tier visuals exist. |  |  | 2026-08-16 16:00 | Doki / SuperDoki / Doki Legend plan modules on creator pages. | Tier visuals exist. Launch tiers will be standardized; exact rules and backend enforcement remain. | Preserved Master Tracker row 72; legacy status: 🔄 In Progress
LEG-MT-073 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Build Store page | In Progress | UI Prototype | Critical | Engineering |  | Close the remaining gap: Launch-critical. |  |  | 2026-08-16 16:00 | Pumdoki Store front-end (Git branch: Store). | Launch-critical. UI prototype exists. Target four noticeable YouTube-like medium thumbnails on common large desktops, with more columns on wider screens. | Preserved Master Tracker row 73; legacy status: 🔄 In Progress
LEG-MT-074 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Build Connect page | In Progress | UI Prototype | Critical | Engineering |  | Build persisted creator discovery with online, price and language filters. Service/order terms need separate definition. |  |  | 2026-09-06 16:00 | Connect is a creator discovery/explore page. It does not itself imply an automated scheduling, booking or fulfillment system. | Founder clarified September 6, 2026. Old full-booking interpretation superseded; launch discovery remains required. | Preserved Master Tracker row 74; legacy status: 🔄 In Progress
LEG-MT-075 | P09 | Real-time messaging and notifications |  | Legacy-mapped task | Real-time messaging and notifications | Build Chat UI | In Progress | UI Prototype | Critical | Engineering |  | Close the remaining gap: Chat UI prototype exists. |  |  | 2026-09-06 16:00 | Real-time direct messaging using authenticated WebSockets. Advanced group/chat features remain post-MVP. | Chat UI prototype exists. Persistence, WebSocket authorization, reconnect, read state, reporting, and rate limits are pending. | Preserved Master Tracker row 75; legacy status: 🔄 In Progress
LEG-MT-077 | P03 | Authentication, roles, and settings | P05, P08 | Legacy-mapped task | Authentication, roles, and settings | Implement NSFW +18 content toggle | In Progress | Backend Implemented | Medium | Engineering |  | Close the remaining gap: Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. |  |  | 2026-08-16 16:00 | User preference to hide or show explicit 18+ content across onboarding, Settings, feeds, search, Store, and Connect. Default hidden. | Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. Onboarding and server-side feed/search/Store/Connect enforcement remain pending. | Preserved Master Tracker row 77; legacy status: 🔄 In Progress
LEG-MT-078 | P03 | Authentication, roles, and settings | P01, P04, P06, P09 | Legacy-mapped task | Authentication, roles, and settings | Build settings page | In Progress | Backend Implemented | High | Engineering |  | Close the remaining gap: Protected Settings is implemented for display name, email/reverification, password, active sessions, and explicit-content preference. |  |  | 2026-08-16 16:00 | Account info, password change, notification preferences, theme toggle (Sakura Kiss / Midnight City), NSFW content toggle, payment/billing section. | Protected Settings implements display name, email/reverification, password, active sessions and explicit-content preference. Theme selection is implemented browser-locally. Account theme sync, real notifications/billing, export and deletion remain pending. | Preserved Master Tracker row 78; legacy status: 🔄 In Progress
LEG-MT-079 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Build help / support page | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Basic FAQ page with accordion answers + simple contact/support form routed to founder inbox. | Plain and functional for MVP. Expands post-launch. | Preserved Master Tracker row 79; legacy status: 📋 Not Started
LEG-MT-080 | P08 | Feed, social actions, Store, and Connect | P03, P05, P06, P07 | Legacy-mapped task | Feed, social actions, Store, and Connect | Build 'Your Activity' page | In Progress | UI Prototype | Medium | Engineering |  | Connect authenticated API and persisted member history after P05/P06/P07. Replace example data when real event sources exist. |  | apps/web/src/pages/ActivityPage.jsx; ActivityPage.test.jsx; tests/e2e/activity.spec.js; PLAN.md §12. | 2026-09-10 16:00 | P08 member history: liked posts, purchases, subscriptions and payment history. UI preview first; account-backed events follow. | Promoted from Post-MVP to P08. /activity preview provides search/category filters and sidebar/header Your Activity links. Example data is explicitly labeled; authenticated account data, API and persistence remain pending. Focused UI tests passed. | Master Tracker row 80; promoted to P08 September 10, 2026. Former duplicate Backlog row 14 cleared.
LEG-MT-081 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Improve Create Post ('Moments') modal | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Replace generic 'What's on your mind?' with Pumdoki-voice copy. Add locked/subscriber-only content state. Improve layout and brand feel. | Basic modal exists. Needs Pumdoki language, locked content toggle, and improved visual polish. | Preserved Master Tracker row 81; legacy status: ✅ Done
LEG-MT-082 | P01 | Repository and frontend foundation |  | Legacy-mapped task | Repository and frontend foundation | Improve side navigation drawer | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Make drawer slightly larger and use darker, more vibrant colors. Currently blends too much into the background — needs presence like Instagram's nav. | Drawer functional but visually weak. Increase icon size, darken colors, improve active state. | Preserved Master Tracker row 82; legacy status: ✅ Done
LEG-MT-083 | P09 | Real-time messaging and notifications |  | Legacy-mapped task | Real-time messaging and notifications | Fix chat: offline avatar + notification badge | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Show creator offline avatar/indicator when creator is offline. Show unread notification badge on minimized chat. Currently missing both. | Chat functional but missing offline state and notification badge on minimized view. | Preserved Master Tracker row 83; legacy status: ✅ Done
LEG-MT-084 | P10 | Creator dashboard |  | Legacy-mapped task | Creator dashboard | Build creator dashboard UI | In Progress | UI Prototype | Low | Engineering |  | Close the remaining gap: Large UI prototype exists. |  |  | 2026-08-16 16:00 | Creator-facing analytics dashboard: revenue chart, active subscribers, profile visits, live activity feed, revenue by source, top performing posts, top fans, quick actions. | Large UI prototype exists. Backend data, actions, reconciliation, and tests remain. Live Streaming stays disabled post-MVP. | Preserved Master Tracker row 84; legacy status: 🔄 In Progress
LEG-MT-085 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Improve landing page posts visuals | Done | Integrated | Low | Engineering |  | No action; reopen only if the approved scope changes. |  |  | 2026-08-16 16:00 | Add a checkmark, a follow buttom, re-arrenge For You / Following and flip sides, add logic to For You (X inspired), | Post visual already in place. Need to add more features and complex logic to the For You page | Preserved Master Tracker row 85; legacy status: ✅ Done
LEG-MT-087 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Define post / content model | In Review | N/A | Medium | Engineering | Targeted review during relevant slice | Local ContentPost/MediaAsset model implemented. Broader content/access design remains In Review. Review revisions, paid audiences and production eligibility before live sensitive use. |  | docs/architecture/phase5-slice1-content-model-and-access-design.md | 2026-09-09 16:00 | Creator posting, visibility flags (public/subscriber/tier-locked), member access rules. | Safe test posts persist locally with sealed bodies/media identities. No paid offers or real creator eligibility. Full content/access design and human review remain open. | Preserved Master Tracker row 87; legacy status: 📋 Not Started
LEG-MT-088 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Build media upload pipeline | In Progress | Backend Implemented | Critical | Engineering | Founder review of working local R2 flow | Review safe photo/video upload, draft reload, publish/member read and removal in the local preview. R2 account, credentials and private access are verified. No deployment or processor approval is implied. |  | HANDOFF.md | 2026-09-09 16:00 | Image/video upload → Cloudflare R2 storage → signed URL delivery. | R2 PNG/MP4 API and browser paths passed, including image display/video playback, private drafts, publish/ranges and removal. API restart preserved posts/session/identical bytes. Public access disabled. All 5 test objects deleted and absence checked. HANDOFF.md. | Preserved Master Tracker row 88; legacy status: 📋 Not Started
LEG-MT-089 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Define public vs private asset rules | In Review | N/A | Medium | Engineering | Targeted review during relevant slice | Local per-request authorization and draft privacy are tested. Review remaining paid entitlements, explicit content and live eligibility before enabling those flows. |  | docs/architecture/phase5-slice1-content-model-and-access-design.md | 2026-09-09 16:00 | Separate teaser, paid, and internal assets with signed URL gating. | Local member reads require an active verified test session. Removal/suspension revoke media access. Disabled by default and rejected in production. Real identity, adult uploads and money remain unavailable. | Preserved Master Tracker row 89; legacy status: 📋 Not Started
LEG-MT-090 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Implement media optimization | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Compress/transcode images and video (thumbnails, adaptive quality). | Needed for smoother UX. | Preserved Master Tracker row 90; legacy status: 📋 Not Started
LEG-MT-091 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Implement watermarking / content protection | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Visible + invisible watermarks to reduce re-sharing risk. | Protection planning in scope. | Preserved Master Tracker row 91; legacy status: 📋 Not Started
LEG-MT-092 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build moderation review flow | Not Started | N/A | High | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Flagged items reviewed and actioned by admin. | Required for platform operations. | Preserved Master Tracker row 92; legacy status: 📋 Not Started
LEG-MT-094 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Integrate CCBill (primary processor) | In Progress | Decision Locked | Medium | Founder | Founder + provider response | Build the functioning review site through the current slices. Return to CCBill when review-ready; merchant approval and technical payment integration remain future work. |  | docs/product/initial-ccbill-inquiry.md; PLAN.md §21; HANDOFF.md safe-content/R2 verification. | 2026-09-10 16:00 | CCBill is the intended primary processor. Sales/site preparation is underway. Formal merchant approval, API/webhooks and subscription billing remain unimplemented. | Inquiry sent and Sales reply received. CCBill requires a fully functioning online site, which may be password protected. The site is being built; no review-ready site, approved account or payment backend is claimed. | Master Tracker row 94; preparation stage reconciled September 10, 2026.
LEG-MT-095 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Integrate Epoch (cascade fallback) | Not Started | N/A | Medium | Founder | Founder + provider response | After core policies/entity details are ready, discuss Epoch fit and any fallback design. Do not implement until the account-specific model is confirmed. |  |  | 2026-09-10 16:00 | Set up Epoch as secondary for transactions CCBill declines. | CCBill review-site preparation is underway. Epoch is an intended fallback only; outreach, approval and integration have not started. | Preserved Master Tracker row 95; legacy status: 📋 Not Started
LEG-MT-096 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Build payment cascading logic | Not Started | N/A | Medium | Engineering | Founder + provider response | Obtain written technical/commercial confirmation from both processors before implementing cascade routing. |  |  | 2026-09-10 16:00 | Route failed CCBill transactions automatically to Epoch before returning decline. | CCBill review-site preparation is underway. No Epoch outreach or account-specific cascade approval is evidenced; routing is unimplemented. | Preserved Master Tracker row 96; legacy status: 📋 Not Started
LEG-MT-097 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Implement recurring subscription billing | Not Started | N/A | High | Engineering | Founder + provider response | Agree the processor-supported payment flow and obtain the required account setup before implementing billing and trusted payment events. |  |  | 2026-09-10 16:00 | Create the actual subscription/payment flow through CCBill/Epoch. | CCBill review-site preparation is underway. Recurring billing and payment-webhook handling are not implemented. | Preserved Master Tracker row 97; legacy status: 📋 Not Started
LEG-MT-098 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Build renewal / cancel logic | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Recurring billing state changes, grace periods, cancellations. | Needed for subscription lifecycle. | Preserved Master Tracker row 98; legacy status: 📋 Not Started
LEG-MT-099 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Tie access gating to subscription status | Not Started | N/A | Critical | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Grant/revoke content access based on active payment state and tier. | Critical premium access control. | Preserved Master Tracker row 99; legacy status: 📋 Not Started
LEG-MT-100 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Define creator payouts flow | Not Started | N/A | High | Founder | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Payout cadence (weekly/biweekly), ledger logic, minimums, admin handling. | Needed once monetization is live. | Preserved Master Tracker row 100; legacy status: 📋 Not Started
LEG-MT-102 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Define platform commission model | Not Started | N/A | High | Founder | Founder + provider response | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Fee structure: platform take rate, creator share, member economics. Founding Creator exception rate must be defined. | Founder decision pending. Model 20/25/30% platform fees against actual processor fees before promising a creator split. | Preserved Master Tracker row 102; legacy status: 📋 Not Started
LEG-MT-103 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Implement chargeback & dispute workflow | Not Started | N/A | Critical | Engineering | Founder + provider response | Define account-specific dispute rules and trusted events, then implement the workflow with private-operations authorization and audit. |  |  | 2026-09-10 16:00 | Track chargebacks from CCBill/Epoch, alert admin, manage dispute responses. | CCBill review-site preparation is underway. Processor dispute integration and operational handling remain unimplemented. | Preserved Master Tracker row 103; legacy status: 📋 Not Started
LEG-MT-104 | POST | Post-MVP |  | Legacy-mapped task | Post-MVP | Plan crypto payment integration | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Research USDT/BTC path. Evaluate self-hosted vs third-party (NowPayments, PayRam). | Deferred; planned as future payment rail. | Preserved Master Tracker row 104; legacy status: 📋 Not Started
LEG-MT-106 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build private operations application | In Progress | UI Prototype | Medium | Engineering | Private-operations security gates | Close the remaining gap: An independently buildable apps/admin shell, public /admin removal, a dormant injected-verifier API seam, and a non-secret readiness packet are merged. |  |  | 2026-08-16 16:00 | Deploy a separately hosted private operations app; do not expose /admin in the public Pumdoki web app. Enforce ADMIN permissions in the API and apply separate operational access controls. | An independently buildable apps/admin shell, public /admin removal, a dormant injected-verifier API seam, and a non-secret readiness packet are merged. No deployed private origin, production verifier, hardware-backed assurance, operator provisioning, origin/CSRF controls, restricted DB grants, or usable review UI exists; G1–G12 are NOT EVALUATED. | Preserved Master Tracker row 106; legacy status: 🔄 In Progress
LEG-MT-107 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build admin overview / operations page | Not Started | N/A | High | Engineering | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Operational snapshot: total users, new signups today, active creators, revenue (gross/net), payout queue, content mod queue count, active flags. | First page you see when logging into admin. Keeps you informed at a glance. | Preserved Master Tracker row 107; legacy status: 📋 Not Started
LEG-MT-108 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build users & creators admin table | Not Started | N/A | Medium | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Searchable table of all accounts. Filter by role (member/creator/admin). View status, join date, spend, earnings. Actions: warn, suspend, ban, verify. | Core operational tool. Needed for day-1 operations. | Preserved Master Tracker row 108; legacy status: 📋 Not Started
LEG-MT-109 | P04 | Legal, trust, and creator onboarding | P11 | Legacy-mapped task | Creator onboarding & trust | Build creator verification & onboarding queue | In Progress | Backend Implemented | Medium | Engineering |  | Close the remaining gap: Application submission/persistence and dormant server-side NEEDS_INFORMATION/REJECTED transitions with successful-transition evidence are merged. |  |  | 2026-08-16 16:00 | Review incoming creator applications. View submitted ID documents. Approve or reject. Log decision with reason. Trigger creator onboarding email. | Application submission/persistence and dormant server-side NEEDS_INFORMATION/REJECTED transitions with successful-transition evidence are merged. No queue/list/detail UI, ID/selfie intake, APPROVED, role promotion, reviewer deployment, notification, or creator publishing exists. | Preserved Master Tracker row 109; legacy status: 🔄 In Progress
LEG-MT-110 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build content moderation queue | Not Started | N/A | Medium | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Queue of all flagged content sorted by severity. Actions: approve, remove, warn creator, escalate. Show content type, creator, flag reason, reporter. | Especially important for NSFW operations. Will be high-volume once platform grows. | Preserved Master Tracker row 110; legacy status: 📋 Not Started
LEG-MT-111 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build reports handling workflow | Not Started | N/A | Medium | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Route user/content reports into admin triage with severity levels (High / Medium / Low). Show open report count, type, and age. | Needed for safety and operations. | Preserved Master Tracker row 111; legacy status: 📋 Not Started
LEG-MT-112 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build payments & payouts admin view | Not Started | N/A | High | Engineering | Founder + provider response | Implement trusted transactions/earnings/payout records and private-operations controls before connecting the admin view. |  |  | 2026-09-10 16:00 | View all transactions, subscription events, payout queue. Manually trigger or block payouts. View CCBill/Epoch transaction IDs. Filter by date, creator, status. | CCBill review-site preparation is underway. Payment/payout backend and this operations view remain unimplemented. | Preserved Master Tracker row 112; legacy status: 📋 Not Started
LEG-MT-113 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build chargeback alert dashboard | Not Started | N/A | Medium | Engineering | Founder + provider response | Confirm processor dispute events and account-specific thresholds before implementing alerts and audited responses. |  |  | 2026-09-10 16:00 | View verified processor chargeback events, calculate rates, apply confirmed account-specific alert thresholds and log authorized dispute responses. | CCBill review-site preparation is underway. No chargeback webhook integration or operational dashboard is implemented. | Preserved Master Tracker row 113; legacy status: 📋 Not Started
LEG-MT-115 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build Founding Badge admin management | Not Started | N/A | High | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | View list of Founding Creators and Founding Members. Track how many slots remain. Assign or revoke badge manually if needed. Show badge count against cap. | Required to manage the founder badge program. Badge count cap enforced here. | Preserved Master Tracker row 115; legacy status: 📋 Not Started
LEG-MT-116 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build admin platform settings panel | Not Started | N/A | High | Engineering | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Configure: platform commission rate, Founding Creator commission rate, NSFW content flags, feature flags (enable/disable features), payout minimums, maintenance mode. | Gives you control over live platform behavior without code deploys. | Preserved Master Tracker row 116; legacy status: 📋 Not Started
LEG-MT-117 | P11 | Admin and moderation | P04 | Legacy-mapped task | Private operations & moderation | Implement 2257 compliance records admin | Not Started | N/A | Critical | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | View and manage age verification records submitted by creators. Link each creator to their ID verification doc. Must be accessible on demand for compliance audits. | Federal requirement. Must be in place before any adult content goes live. | Preserved Master Tracker row 117; legacy status: 📋 Not Started
LEG-MT-118 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Implement audit log | Not Started | N/A | Medium | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Track all admin actions with timestamp, admin user, action type, and affected entity. Immutable log — no deleting entries. | The merged creator-review event records successful non-approval transitions at application level, but it is not a complete immutable operations audit. The global audit log, restricted audit destination, retention, and operational evidence controls remain unimplemented. | Preserved Master Tracker row 118; legacy status: 📋 Not Started
LEG-MT-120 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Define analytics event tracking | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Track signups, subscriptions, content views, conversions, churn signals. | Needed before beta/public launch. | Preserved Master Tracker row 120; legacy status: 📋 Not Started
LEG-MT-121 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Build launch KPI dashboard | Not Started | N/A | Medium | Engineering | Private-operations security gates | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Lightweight internal reporting view for admin. | Needed to monitor launch health. | Preserved Master Tracker row 121; legacy status: 📋 Not Started
LEG-MT-122 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Set up support / contact workflow | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Route issues to a manageable inbox (email-based initially). | Needed for operational readiness. | Preserved Master Tracker row 122; legacy status: 📋 Not Started
LEG-MT-123 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Create FAQ / help center content | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Common setup, billing, and policy answers. | Useful before public launch. | Preserved Master Tracker row 123; legacy status: 📋 Not Started
LEG-MT-124 | P09 | Real-time messaging and notifications | P03, P04, P06 | Legacy-mapped task | Real-time messaging and notifications | Implement notifications / email system | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Provider-neutral console/SMTP delivery, local Mailpit, and verification/password-reset messages are implemented. |  |  | 2026-08-16 16:00 | Transactional emails (welcome, billing, reset) and platform notices via SES or Resend/Postmark. | Provider-neutral console/SMTP delivery, local Mailpit, and verification/password-reset messages are implemented. Production provider selection, adult-business fit, deliverability/authentication, billing/moderation/booking mail, and platform notifications remain open. | Preserved Master Tracker row 124; legacy status: 🔄 In Progress
LEG-MT-126 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Recruit initial creators | Not Started | N/A | Medium | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Secure first launch or beta creators. | Needed for a credible launch marketplace. | Preserved Master Tracker row 126; legacy status: 📋 Not Started
LEG-MT-127 | P14 | QA, security, private beta, and launch | P04 | Legacy-mapped task | Quality, beta & launch readiness | Create creator onboarding docs | Not Started | N/A | Medium | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | How-to for setup, posting, pricing, tier themes, and policy. | Helpful for beta and early launch. | Preserved Master Tracker row 127; legacy status: 📋 Not Started
LEG-MT-128 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Define beta member invite list | Not Started | N/A | Medium | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Choose initial users to test flows. | Needed for private beta. | Preserved Master Tracker row 128; legacy status: 📋 Not Started
LEG-MT-129 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Build waitlist / lead capture | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Collect early interest before public release. | Useful for launch momentum. | Preserved Master Tracker row 129; legacy status: 📋 Not Started
LEG-MT-130 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Create social launch content plan | Not Started | N/A | High | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Posts, teasers, launch announcements. | Needed before public launch. | Preserved Master Tracker row 130; legacy status: 📋 Not Started
LEG-MT-131 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Define referral / affiliate plan | Not Started | N/A | Medium | Founder |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Lightweight growth loop for early users. | Can be simple but useful. | Preserved Master Tracker row 131; legacy status: 📋 Not Started
LEG-MT-132 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Build Pumdoki Discord Server | In Progress | Decision Locked | High | Founder |  | Close the remaining gap: Needed before public launch. |  |  | 2026-08-16 16:00 | Marketing tool to build audience, recruit our first creators, and create a community. | Needed before public launch. | Preserved Master Tracker row 132; legacy status: 🔄 In Progress
LEG-MT-134 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Build internal QA checklist | In Progress | Decision Locked | High | Engineering |  | Close the remaining gap: Repository checks and real-stack browser coverage are established, including merged routing, auth, Settings, and creator-application flows. |  |  | 2026-08-16 16:00 | Turn roadmap into a structured test list. | Repository checks and real-stack browser coverage are established, including merged routing, auth, Settings, and creator-application flows. The broader product, beta, payment, moderation, and launch QA checklist remains incomplete. | Preserved Master Tracker row 134; legacy status: 🔄 In Progress
LEG-MT-135 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Plan private beta | Not Started | N/A | Medium | Founder |  | Define beta testing and its payment method with the relevant functional slice. No payment implementation alternative is selected. |  |  | 2026-09-09 16:00 | Define who tests, what gets tested, how feedback is captured. | Launch features and live-use controls remain applicable. Beta payment method is unresolved. | Preserved Master Tracker row 135; legacy status: 📋 Not Started
LEG-MT-136 | P14 | QA, security, private beta, and launch | P07 | Legacy-mapped task | Quality, beta & launch readiness | Run end-to-end flow testing | Not Started | N/A | High | Engineering | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Test signup → content → subscription → gating → payout → admin. | Needed after core build is ready. | Preserved Master Tracker row 136; legacy status: 📋 Not Started
LEG-MT-137 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Run security review | Not Started | N/A | High | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Auth, media access, role checks, secrets, signed URLs, abuse risks. | Needed before public launch. | Preserved Master Tracker row 137; legacy status: 📋 Not Started
LEG-MT-138 | P14 | QA, security, private beta, and launch | P06 | Legacy-mapped task | Quality, beta & launch readiness | Run payment flow testing | Not Started | N/A | Critical | Engineering | Founder + provider response | Test the agreed implemented payment flow in the appropriate provider test environment. Include cascade only after written confirmation. |  |  | 2026-09-10 16:00 | CCBill → Epoch cascade, subscription lifecycle, renewal, cancel, chargebacks. | CCBill review-site preparation is underway. No payment integration exists to test yet; no passing payment tests are claimed. | Preserved Master Tracker row 138; legacy status: 📋 Not Started
LEG-MT-139 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Prepare soft-launch go/no-go checklist | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Define criteria for a limited launch. | Useful before broad release. | Preserved Master Tracker row 139; legacy status: 📋 Not Started
LEG-MT-140 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Prepare public launch checklist | Not Started | N/A | High | Engineering | Counsel / founder decision | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Confirm readiness: product, legal, payments, support, marketing. | Final pre-launch checkpoint. | Preserved Master Tracker row 140; legacy status: 📋 Not Started
LEG-MT-141 | P14 | QA, security, private beta, and launch |  | Legacy-mapped task | Quality, beta & launch readiness | Define post-launch bug triage process | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Severity rules and response rhythm for launch issues. | Needed once public users arrive. | Preserved Master Tracker row 141; legacy status: 📋 Not Started
LEG-MT-145 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Implement tipping / Send Love | Not Started | N/A | Critical | Engineering |  | Define tipping funding with the beta payment method and processor terms. |  |  | 2026-09-09 16:00 | Tipping/Send Love remains launch scope. Paid flows need idempotent payment evidence, creator earnings and refund controls. | Historically moved from backlog into launch scope. Beta payment method remains unresolved. | Preserved Master Tracker row 145; legacy status: 📋 Not Started
LEG-MT-146 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Implement PPV purchases | Not Started | N/A | Medium | Engineering |  | Define PPV funding with the beta payment method and processor terms. Preserve durable entitlements and reconciliation. |  |  | 2026-09-09 16:00 | Unlock individual photos/videos or bundles using the agreed beta payment method, with durable asset-level entitlements. | Historically moved from backlog into launch scope. Payment method remains unresolved. | Preserved Master Tracker row 146; legacy status: 📋 Not Started
LEG-MT-147 | P09 | Real-time messaging and notifications |  | Legacy-mapped task | Real-time messaging and notifications | Implement real-time WebSocket messaging | Not Started | N/A | Critical | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-09-06 16:00 | Authenticated direct messages with persistence, reconnect, read states, presence, rate limits, block, and report. | Basic real-time DMs are launch scope; advanced group/chat features remain post-MVP. | Preserved Master Tracker row 147; legacy status: 📋 Not Started
LEG-MT-148 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Complete Store for launch | In Progress | UI Prototype | High | Engineering |  | Close the remaining gap: UI prototype exists; backend and payment integration remain. |  |  | 2026-08-16 16:00 | Connect Store tabs, search, purchase, history, favorites, liked content, filters, and responsive four-card desktop presentation to real data. | UI prototype exists; backend and payment integration remain. | Preserved Master Tracker row 148; legacy status: 🔄 In Progress
LEG-MT-149 | P08 | Feed, social actions, Store, and Connect |  | Legacy-mapped task | Feed, social actions, Store, and Connect | Complete Connect for launch | In Progress | UI Prototype | Critical | Engineering |  | Build persisted creator discovery with online, price and language filters. Service/order terms need separate definition. |  |  | 2026-09-06 16:00 | Connect is a creator discovery/explore page. It does not itself imply an automated scheduling, booking or fulfillment system. | Founder clarified September 6, 2026. Old full-booking interpretation superseded; launch discovery remains required. | Preserved Master Tracker row 149; legacy status: 🔄 In Progress
LEG-MT-150 | P12 | Oasis/Drimy launch implementation |  | Legacy-mapped task | Oasis/Drimy launch implementation | CANCELLED: old Oasis / Drimy game | Deferred | UI Prototype | Low | Engineering | Cancelled by founder | Do not implement this legacy game. Future streak/language concept is separate and post-launch. |  |  | 2026-09-06 16:00 | Create server-authoritative Drimy ownership, XP, Orbs, tasks, evolution, inventory, achievements, and daily resets. | Cancelled September 6, 2026. Historical specification retained in Scope/Description and preserved Master Tracker. This is not a launch dependency. | Preserved Master Tracker row 150; legacy status: 🔄 In Progress
LEG-MT-151 | P12 | Oasis/Drimy launch implementation |  | Legacy-mapped task | Oasis/Drimy launch implementation | CANCELLED: old Oasis game collectibles | Deferred | N/A | Low | Engineering | Cancelled by founder | Do not implement this legacy game. Future streak/language concept is separate and post-launch. |  |  | 2026-09-06 16:00 | Create collectible backgrounds, skins, frames, badges, equipped states, fixed-price store items, and reward inventory. | Cancelled September 6, 2026. Historical specification retained in Scope/Description and preserved Master Tracker. This is not a launch dependency. | Preserved Master Tracker row 151; legacy status: 📋 Not Started
LEG-MT-152 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Implement explicit-content preference | In Progress | Decision Locked | Medium | Engineering |  | Close the remaining gap: Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. |  |  | 2026-08-16 16:00 | Add hide/show 18+ content choice to onboarding, Settings, feed, search, Store, and Connect; default hidden. | Default-hidden preference persistence and protected Settings opt-in/immediate opt-out are implemented and CI-verified. Onboarding and server-side feed/search/Store/Connect enforcement remain pending. | Preserved Master Tracker row 152; legacy status: 🔄 In Progress
LEG-MT-153 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Define international launch allowlist | Not Started | N/A | High | Engineering | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Enable countries only after payment, payout, identity, adult-content law, privacy, tax, sanctions, and support review. | Prioritize USA and selected Latin American countries; phase EU/EEA carefully. | Preserved Master Tracker row 153; legacy status: 📋 Not Started
LEG-MT-154 | P04 | Legal, trust, and creator onboarding | P06, P13 | Legacy-mapped task | Creator onboarding & trust | Support Latin American creator onboarding | Not Started | N/A | High | Engineering | Founder + counsel/provider | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Plan Spanish localization, local IDs, tax residency, payout support, time zones, and region-appropriate assistance. | Core creator acquisition requirement. | Preserved Master Tracker row 154; legacy status: 📋 Not Started
LEG-MT-155 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Creator onboarding & trust | Select identity verification approach | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Compare specialist providers and a tightly controlled manual-beta workflow; design for later provider migration. | Manual review requires encrypted isolated storage, strict access, and audit logs. | Preserved Master Tracker row 155; legacy status: 📋 Not Started
LEG-MT-156 | P05 | Media pipeline and content model |  | Legacy-mapped task | Media pipeline and content model | Define initial media upload limits | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Start with cost-conscious limits and direct R2 uploads; measure beta storage/transcoding cost before raising limits. | Provisional: images 20 MB, video 1 GB/30 min, audio 250 MB, ID files 10 MB. | Preserved Master Tracker row 156; legacy status: 📋 Not Started
LEG-MT-157 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Select transactional email provider | Not Started | N/A | Medium | Engineering |  | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Evaluate Amazon SES first, verify adult-business support, and implement verification, reset, billing, moderation, and booking mail. | Provider-neutral SMTP/console abstraction and local Mailpit are implemented. Production provider selection, adult-business support, deliverability, TLS, DKIM, SPF, and DMARC remain open. | Preserved Master Tracker row 157; legacy status: 📋 Not Started
LEG-MT-158 | P04 | Legal, trust, and creator onboarding |  | Legacy-mapped task | Legal & compliance | Complete Maryland LLC formation | In Progress | N/A | Medium | Founder | Northwest / state approval | Await Maryland approval and approved documents. Filing is reported complete; exact filing date/ID, EIN, bank setup and actual invoice remain unverified. |  |  | 2026-09-08 16:00 | Maryland LLC selected and filing reported by founder for Kiban Digital Holdings LLC through Northwest. Record approved filing and address details once returned. | Founder reported filing complete September 8, 2026; this is the report date, not a verified filing date. State approval pending. Filing ID and actual cost were not supplied. | Preserved Master Tracker row 158; legacy status: 📋 Not Started
LEG-MT-159 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Decide commission and payout model | Not Started | N/A | High | Founder | Founder + provider response | Confirm dependencies and owner, then define the first deliverable. |  |  | 2026-08-16 16:00 | Model processor fees, chargebacks, refunds, taxes, platform fee, Founding Creator discount, payout cadence, and minimum. | Do not publish the current 80/20 mock copy until actual processor economics are known. | Preserved Master Tracker row 159; legacy status: 📋 Not Started
LEG-MT-160 | P11 | Admin and moderation |  | Legacy-mapped task | Private operations & moderation | Define private operations architecture | In Progress | Backend Implemented | Medium | Engineering | Private-operations security gates | Close the remaining gap: A separate apps/admin shell, dormant injected-verifier review seam, and merged non-secret G1–G12 readiness packet exist. |  |  | 2026-08-16 16:00 | Build a separately deployed private operations application with API-enforced ADMIN permissions, stronger access controls, sensitive-record permissions, and immutable audit logging. | A separate apps/admin shell, dormant injected-verifier review seam, and merged non-secret G1–G12 readiness packet exist. The router is unmounted; production authentication, restricted hosting, phishing-resistant hardware-backed assurance, operator provisioning, origin/CSRF controls, trusted-proxy handling, restricted DB grants, immutable audit, and deployment are absent; all gates are NOT EVALUATED. | Preserved Master Tracker row 160; legacy status: 🔄 In Progress
LEG-MT-161 | P02 | Backend and database foundation |  | Legacy-mapped task | Backend and database foundation | Adopt TypeScript backend and shared contracts | In Progress | UI Prototype | Medium | Engineering |  | Close the remaining gap: TypeScript API/contracts/database foundations now cover auth, protected Settings, creator applications, and the dormant review seam; frontend conversion remains incremental. |  |  | 2026-08-16 16:00 | Keep the current web prototype in JavaScript initially; write new API/database/contracts in TypeScript and migrate frontend gradually. | TypeScript API/contracts/database foundations now cover auth, protected Settings, creator applications, and the dormant review seam; frontend conversion remains incremental. | Preserved Master Tracker row 161; legacy status: 🔄 In Progress
LEG-MT-162 | P00 | Baseline, tracker, and scope control | P04 | Legacy-mapped task | Baseline, tracker, and scope control | Replace prototype contact addresses | Done | N/A | High | Engineering | Counsel / founder decision | Publish truthful prototype cleanup with the next approved website release. Final legal/contact copy follows counsel approval and operational proof. |  | https://github.com/QK-Connoisseur/PDoki/commit/56cb0adaffa4896aa9d54257b4eecfe18804bb54 | 2026-09-06 16:00 | Replace unconfigured production-looking emails with .example sample addresses until real domains and mailboxes are operational. | Prototype legal claims and unconfigured production-looking contacts corrected and pushed to dev in 56cb0ad. Final CI/main publication evidence is in HANDOFF.md. A source merge does not deploy the website or establish final policies. | Preserved Master Tracker row 162; legacy status: 📋 Not Started
LEG-MT-163 | P14 | QA, security, private beta, and launch | P04 | Legacy-mapped task | Quality, beta & launch readiness | Prepare public-member / controlled-creator beta | In Progress | Decision Locked | High | Founder | Founder + counsel/provider | Close the remaining gap: Public member registration exists, while creator applications remain PENDING and identity NOT_STARTED. |  |  | 2026-08-16 16:00 | Allow public member registration when safe while onboarding creators through verification and approval controls. | Public member registration exists, while creator applications remain PENDING and identity NOT_STARTED. No approval, role promotion, identity/tax/banking intake, deployed reviewer workflow, or creator publishing gate exists; controlled beta readiness remains incomplete. | Preserved Master Tracker row 163; legacy status: 🔄 In Progress
LEG-MT-164 | P06 | Payments, subscriptions, tipping, and PPV |  | Legacy-mapped task | Payments & entitlements | Confirm CCBill → Epoch cascade | Not Started | N/A | High | Founder |  | Obtain written account-specific technical and commercial confirmation from CCBill and Epoch before any fallback implementation. |  |  | 2026-09-10 16:00 | Obtain written technical and commercial confirmation before implementing fallback payment routing. | CCBill Sales has replied and site preparation is underway. Epoch outreach and cascade confirmation remain pending. | Preserved Master Tracker row 164; legacy status: 📋 Not Started
P00-T03 | P00 | Baseline, tracker, and scope control |  | PLAN task | Tracker & scope control | Reclassify the tracker to PLAN.md Phases 0–14 | Done | N/A | High | Engineering |  | Use the PLAN-aligned tracker as the operating view and keep owners, dates, evidence, and daily debriefs current. |  | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00 | Make PLAN.md the phase source of truth and separate workflow from maturity. | Published through PR #13. No legacy task, note, backlog item, assumption, or expense value was deleted. | PLAN.md Phase 0 task 3
P02-T11 | P02 | Backend and database foundation |  | PLAN task | Durable async work | Add a background-job queue | Done | Backend Implemented | High | Engineering |  | Keep the foundation canary-only while deployment, monitoring, Redis/shared throttling, general idempotency, and product-flow migrations remain separately gated. |  | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00 | Production-shaped durable job migration, separate worker process, leases, retry, terminal handling, telemetry, and a fixed canary. | Published through PR #13 as a foundation only; no product flow, provider, deployment, or live credentials were added. | PLAN.md Phase 2 task 11
P02-T12A | P02 | Backend and database foundation | P14 | Supplemental | Durable async work | Prove canary-specific idempotency and lease fencing | Done | Backend Implemented | High | Engineering |  | Treat this as canary-specific evidence only; design the reusable consequential-operation idempotency framework in a separately approved slice. |  | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00 | Canary-specific idempotency proof supporting the durable worker foundation. | Published through PR #13. This does not implement the reusable product-wide idempotency framework. | Supports PLAN.md Phase 2 task 12
P02-T12B | P02 | Backend and database foundation |  | PLAN task | Idempotency | Add a reusable general idempotency framework | Not Started | Decision Locked | High | Engineering | Separate implementation approval | Define the first consequential product operation only after the worker foundation is reviewed and merged. |  | https://github.com/QK-Connoisseur/PDoki/blob/dev/docs/architecture/phase2-async-work-throttling-idempotency.md | 2026-08-21 16:00 | PostgreSQL-backed durable idempotency with explicit in-progress/completed recovery semantics. | PR #13 proves only a non-secret canary and does not authorize product-flow migration. | PLAN.md Phase 2 task 12
P02-T10R | P02 | Backend and database foundation | P03 | Supplemental | Shared throttling | Implement Redis-backed shared throttling with bounded outage behavior | Not Started | Decision Locked | High | Engineering | Separate implementation approval + topology decision | Define exact route thresholds and the approved outage fallback before adding Redis. |  | https://github.com/QK-Connoisseur/PDoki/blob/dev/docs/architecture/phase2-async-work-throttling-idempotency.md | 2026-08-21 16:00 | Redis is limited to shared throttling and ephemeral coordination; unlimited outage behavior is prohibited. | No Redis dependency or shared store is included in PR #13. | Completes PLAN.md Phase 2 task 10 across replicas
P02-NET-001 | P02 | Backend and database foundation |  | Supplemental | Local security | Bind local PostgreSQL host exposure to IPv4 loopback | Done | Backend Implemented | High | Engineering |  | Preserve the 127.0.0.1-only local default; deployed network controls and restricted credentials remain separate gates. |  | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00 | Reduce LAN exposure of the local static-development database credential. | Published through PR #13 as local-only hardening; no staging or production configuration changed. | PR #13 supplemental hardening
P04-S1 | P04 | Legal, trust, and creator onboarding | P03 | Published slice | Creator onboarding & trust | Publish the creator-application submission foundation | Done | Integrated | High | Engineering |  | Preserve the PENDING-only, no-role-promotion boundary until later trust and legal gates are approved. |  | https://github.com/QK-Connoisseur/PDoki/commit/ce6c9e4 | 2026-08-21 16:00 | Verified members can submit one persisted creator application with versioned prototype acceptances recorded atomically. | Published Phase 4 Slice 1; no identity files, approval, creator role promotion, or Dashboard access. | PLAN.md Phase 4 published foundation
P04-S2 | P04 | Legal, trust, and creator onboarding | P11 | Published slice | Private operations & moderation | Publish the dormant non-approval review-transition foundation | Done | Backend Implemented | High | Engineering |  | Keep the router unmounted and APPROVED/role-promotion behavior absent until the documented activation gates are satisfied. |  | https://github.com/QK-Connoisseur/PDoki/pull/1 | 2026-08-21 16:00 | Persist strict non-approval review transitions and immutable reviewer evidence in one transaction. | Published Phase 4 Slice 2 foundation; deliberately not an operational admin workflow. | PLAN.md Phase 4 published foundation
P07-E2E-001 | P07 | Core end-to-end vertical slice | P04, P05, P06 | PLAN phase gate | Core vertical slice | Complete the member-to-creator end-to-end product flow | Blocked | N/A | High | Engineering | Phase 4–6 dependencies | Continue controlled test slices. Real beta needs applicable creator/content/access/operations controls. Paid flows also need processor evidence and reconciliation. |  | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#11-phase-7--core-end-to-end-vertical-slice | 2026-09-09 16:00 | Member discovers an eligible creator and accesses authorized content with auditable records. Purchases and tips follow the beta payment method, still unresolved. | Phase 7 remains incomplete. Payment, entitlement, earnings and refund controls remain necessary for paid beta flows. | PLAN.md Phase 7 exit gate
P14-QA-001 | P14 | QA, security, private beta, and launch | P08 | Supplemental | Deterministic E2E | Make promotion material E2E independent of calendar date | Done | Integrated | Medium | Engineering |  | Keep calendar-dependent fixtures under an explicit test clock and retain the real-stack Playwright regression. |  | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00 | Freeze the test clock without changing product or fixture behavior. | Published through PR #13 after exact-head and post-merge CI passed; no product or fixture behavior changed. | PR #13 CI repair
P04-OPS-001 | P04 | Legal, trust, and creator onboarding | P11 | Supplemental | Private operations & moderation | Verify signed private-operations assertions | Done | Backend Implemented | Critical | Engineering |  | Preserve the dormant boundary. Additional operations work is parked; production activation requires its applicable controls. |  | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00 | Provider-neutral signed assertion verification for the dormant private-operations boundary. | Slice 3 merged through PR #15. Local foundation completed; public router remains unmounted. No operational approval, role promotion, identity collection or deployment. | Supports PLAN Phase 4 and the Phase 11 private-operations dependency.
P04-OPS-002 | P04 | Legal, trust, and creator onboarding | P11 | Supplemental | Private operations & moderation | Enforce explicit operator provisioning and transaction-time authorization | Done | Backend Implemented | Critical | Engineering |  | Preserve the dormant boundary. Additional operations work is parked; production activation requires its applicable controls. |  | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00 | Database-owned operator identity and permission evidence for dormant non-approval reviews. | Slice 3 merged through PR #15. Local foundation completed; public router remains unmounted. No operational approval, role promotion, identity collection or deployment. | Supports PLAN Phase 4 and the Phase 11 private-operations dependency.
P04-OPS-003 | P04 | Legal, trust, and creator onboarding | P11 | Supplemental | Private operations & moderation | Verify the dormant private request-integrity boundary | Done | Backend Implemented | High | Engineering |  | Preserve the dormant boundary. Additional operations work is parked; production activation requires its applicable controls. |  | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00 | Test-only request-integrity composition and safe audit evidence for the unmounted operations router. | Slice 3 merged through PR #15. Local foundation completed; public router remains unmounted. No operational approval, role promotion, identity collection or deployment. | Supports PLAN Phase 4 and the Phase 11 private-operations dependency.

## Review & Blocker Queue
🔎 Pumdoki Review & Blocker Queue
Focused view derived from Delivery Tracker. Update the canonical source row there; use this sheet for daily review and blocker triage.
Work ID | Phase | PLAN Phase | Workstream | Work Item | Workflow | Owner | Waiting On / Reviewer | Next Action | Next Check | Evidence | Updated
DEC-CCBILL | P06 | Payments and payouts | Cancelled clarification follow-up only | Do not send this cancelled follow-up | Deferred | Founder |  | Deferred applies only to this cancelled clarification. CCBill Sales/site preparation is in progress; the current founder task remains local content-flow review. Account-specific approval and payment integration remain unresolved. |  | docs/product/initial-ccbill-inquiry.md | 2026-09-10 16:00
DEC-LEGAL-UI-TRUTH | P04 | Legal, trust, and creator onboarding | Truthful prototype copy | Release verified legal UI cleanup | Deferred | Engineering | Approved website release | Cleanup source is pushed to dev in 56cb0ad. Deploy in an approved website release; final counsel policies and actual processes remain future work. CI/main evidence is in HANDOFF.md. |  | https://github.com/QK-Connoisseur/PDoki/commit/56cb0adaffa4896aa9d54257b4eecfe18804bb54 | 2026-09-06 16:00
P04-S4-RECONCILE | P04 | Legal, trust, and creator onboarding | Branch reconciliation | Slice 4 source published to dev | Done | Engineering |  | PR #17 merged through dev 56cb0ad, preserving 317abda/25057bd ancestry. Final CI and main-publication evidence is in HANDOFF.md; no deployment or operations activation is implied. |  | https://github.com/QK-Connoisseur/PDoki/pull/17 | 2026-09-06 16:00
P07-E2E-001 | P07 | Core end-to-end vertical slice | Core vertical slice | Complete the member-to-creator end-to-end product flow | Blocked | Engineering | Applicable beta flow dependencies | Continue safe test slices. Beta payment method is unresolved. Paid flows still need processor, entitlement, earnings, refund and reconciliation controls. |  | https://github.com/QK-Connoisseur/PDoki/blob/dev/PLAN.md#11-phase-7--core-end-to-end-vertical-slice | 2026-09-09 16:00
LEG-MT-087 | P05 | Media pipeline and content model | Content and access design | Review P05 Slice 1 local design | In Review | Engineering | Targeted review during relevant slice | Broader design remains In Review. The local safe-content slice is implemented and under verification. Targeted review is still required before live sensitive use. No P05 exit, deployment or provider approval is claimed. |  | docs/architecture/phase5-slice1-content-model-and-access-design.md | 2026-09-09 16:00

## Daily Log
📅 Pumdoki Daily Progress Log
Append one row per meaningful work session. This is the history behind the plain-language debrief; never rewrite earlier entries.
Date | Work ID | Phase | Goal | What Changed | Why It Matters | What Did Not Change | Verification / Evidence | Status After | Approval / Blocker | Next Step | Logged By
2026-08-21 16:00 | P02-T11 | P02 | Build a reliable local worker foundation. | Added the PostgreSQL durable-job foundation, separate worker process, lease fencing, retry/terminal behavior, aggregate telemetry, and a fixed non-secret canary in draft PR #13. | Later asynchronous product work can use a reviewed durable base instead of ad-hoc request-time delivery. | No product flow, provider, deployment, Redis, live credentials, email/token migration, payment, identity or creator-review activation. | https://github.com/QK-Connoisseur/PDoki/pull/13 — baseline exact-head CI run 32442777168 passed before this tracker update; fresh CI is required. | In Review | Merge remains separately gated. | Review the updated PR and require fresh exact-head CI. | Codex
2026-08-21 16:00 | P14-QA-001 | P14 | Remove a calendar-date E2E failure. | Fixed the promotion-material Playwright test to use a fixed clock before navigation. | The test no longer fails when promotion fixtures pass their wall-clock expiry date. | No application or fixture behavior changed. | https://github.com/QK-Connoisseur/PDoki/pull/13 | In Review | Fresh CI required after the tracker commit. | Confirm all three PR checks pass on the new head. | Codex
2026-08-21 16:00 | P00-T03 | P00 | Make the tracker match PLAN.md and support daily debriefs. | Mapped all 148 legacy tasks into PLAN Phases 0–14, added stable IDs, roadmap/decision/daily views, and preserved the legacy tracker and notes. | Founder and engineering can now see current work, review state, blockers, maturity, evidence, and next actions without reading every technical record. | No legacy task, note, backlog item, assumption, or expense value was deleted or silently changed. | https://github.com/QK-Connoisseur/PDoki/pull/13 | In Review | Founder review; merge separately gated. | Use the new Delivery Tracker and Daily Log as the operating views. | Codex
2026-08-21 16:00 | P02-T11 | P02 | Publish and reconcile the Phase 2 worker foundation. | PR #13 merged into dev as 6311522 from reviewed head 8a8688f; post-merge CI 32535922437 passed all three jobs, and the five scoped tracker records moved from In Review to Done. | The durable canary foundation and PLAN-aligned tracker are now published, and the operating views accurately separate completed evidence from the remaining Phase 2 and Phase 4 gates. | No product flow, provider, Redis store, deployment, live credential, creator approval, role promotion, or private-operations activation was added. | https://github.com/QK-Connoisseur/PDoki/pull/13 · https://github.com/QK-Connoisseur/PDoki/actions/runs/32535922437 | Done | Any new implementation and this reconciliation branch's publication remain separately gated. | Seek a separate decision on the Phase 4 private-operations identity/access design and local verification scope. | Codex
2026-08-23 16:00 | P04-OPS-001 | P04 | Build a dormant private-operations identity/access foundation. | Added strict signed-assertion verification, DB-owned exact operator mappings and permission grants, transaction-time reauthorization, request-integrity seams, immutable history protections, and direct-peer/redacted audit evidence. | The next operations review work can be evaluated against production-shaped local trust-boundary primitives instead of trusting injected identities or caller-supplied permissions. | The review router remains unmounted. No APPROVED transition, role promotion, identity collection/files, live provider or issuer, operations session/server, private origin, runtime DB roles, deployment, or live configuration was added; G1–G12 remain NOT EVALUATED. | https://github.com/QK-Connoisseur/PDoki/blob/codex/phase4-private-ops-access-foundation/docs/architecture/phase4-slice3-private-operations-access-foundation.md · implementation commit 9904334 · 287 API / 166 web / 24 contracts / 15 focused DB-review tests | In Review | Draft-PR publication is authorized; merge and every activation/deployment step remain separately gated. | Publish the draft PR, require exact-head CI, and review the dormant trust boundary without activation. | Codex
46271.6667 | DEC-SEQUENTIAL | P00 | Record founder launch corrections and funding limits. | Retained Connect discovery, real-time chat and tipping; cancelled the old Oasis game; recorded post-launch streak concept, provisional founding/Plus offers and staged cash budget. | The next founder task is the initial business definition, with no spending required. | No provider selected, public benefit promised, purchase made, deployment or activation authorized by this budget. | Founder decision, September 6, 2026; Launch Budget; Decision Register | Done | Qualified service quotes and commercial terms remain open. | Complete the one-page initial business definition. | Codex
2026-09-08 16:00 | LEG-MT-087 | P05 | Draft P05 Slice 1 content model and access rules. | Prepared a local content/revision/media/offer model, lifecycle, access rules and synthetic acceptance cases. Definition tasks LEG-MT-087 and LEG-MT-089 are In Review. | Creates a concrete design for review before the first protected-media implementation. | No contracts, migrations, API routes, worker handlers or UI changed. P05 backend and phase exits remain unfinished; no upload, payment or live operations activated. | docs/architecture/phase5-slice1-content-model-and-access-design.md | In Review | Scoped human technical review remains pending. | Review the design. Founder still awaits the sent CCBill inquiry response and Maryland formation approval. | Codex

## Decision Register
🔐 Pumdoki Decision & Dependency Register
Founder, legal, provider, and infrastructure decisions that block or constrain delivery. Targets are management review dates, not legal deadlines.
Decision ID | Phase | Decision / Dependency | Owner | Target | Workflow | Current State | Next Action | Evidence | Updated
DEC-AWS-STAGING | P02 | AWS staging shape and account access | Founder | 2026-07-23 16:00 | Blocked | Deployment shape, credentials boundary, and approval remain undecided. | Review the provider-neutral staging matrix and explicitly approve a staging-only shape. | https://github.com/QK-Connoisseur/PDoki/tree/dev/docs/operations | 2026-08-21 16:00
DEC-MONITORING | P02 | Sentry or equivalent | Founder | 2026-07-23 16:00 | Blocked | Provider, environment separation, PII minimization, retention, alerting, and cost remain undecided. | Select a provider only after reviewing the scorecard and data boundaries. | https://github.com/QK-Connoisseur/PDoki/tree/dev/docs/operations | 2026-08-21 16:00
DEC-ASYNC-ARCH | P02 | Redis, queue, and idempotency architecture | Engineering | 2026-08-18 16:00 | Done | PostgreSQL is durable truth; Redis is limited to shared throttling/ephemeral coordination; unlimited outage behavior is prohibited. | Preserve the ADR constraints during implementation. | https://github.com/QK-Connoisseur/PDoki/blob/dev/docs/architecture/phase2-async-work-throttling-idempotency.md | 2026-08-21 16:00
DEC-WORKER-PR13 | P02 | Application-owned worker foundation review | Founder | 2026-08-25 16:00 | Done | PR #13 merged into dev as 6311522 from reviewed head 8a8688f; exact-head and post-merge CI passed all three jobs. | Preserve the fixed-canary and no-product-flow boundary; treat every further Phase 2 implementation or deployment step as separately gated. | https://github.com/QK-Connoisseur/PDoki/pull/13 | 2026-08-21 16:00
DEC-EMAIL | P09 | Transactional email provider | Founder |  | Deferred | Local Mailpit and provider-neutral mail exist. Production startup correctly fails closed without approved delivery. | Choose email after entity, processor fit, country/data boundaries and funded staging scope are known. Configure and test sender authentication, bounce handling and delivery before external account flows. | https://github.com/QK-Connoisseur/PDoki/tree/dev/docs/operations | 2026-09-06 16:00
DEC-LLC | P04 | Maryland LLC filed; approval pending | Founder |  | In Progress | Kiban Digital Holdings LLC is reported filed in Maryland through Northwest; state approval pending. Founder confirmed $196 total paid, recorded in Expense Tracker. Filing ID, EIN and bank readiness remain unverified. | Await Maryland approval and approved documents; record invoice when available. Continue the planned P05 test-content flow while handling only the founder/provider decisions that slice needs. | Founder reports: filing/inquiry sent September 8; CCBill Sales reply supplied September 9; $196 formation total confirmed September 10. State approval and exact correspondence times remain unverified. | 2026-09-10 16:00
DEC-CCBILL | P06 | Preliminary CCBill model fit and costs | Founder |  | In Progress | CCBill Sales replied: fully functioning online site required; password protection allowed. Site work is underway, including verified safe-content/R2 flow and commissioned policies. Model fit, fees/reserves, payouts and approval remain open. | Keep the current founder step: review the working local content flow. Continue site slices and return to Sales when review-ready. The clarification follow-up remains cancelled; payment backend is not implemented. | User-pasted CCBill Sales reply supplied September 9, 2026; sender timestamp not verified. docs/product/initial-ccbill-inquiry.md | 2026-09-10 16:00
DEC-IDENTITY | P04 | Identity-verification shortlist | Founder | 2026-07-30 16:00 | Blocked | Provider/manual-beta choice, DPA, retention, countries, and security are open. | Compare two or three providers and a controlled manual-beta boundary. |  | 2026-08-21 16:00
DEC-EPOCH | P06 | Epoch terms and written cascade behavior | Founder | 2026-08-06 16:00 | Blocked | Commercial and technical fallback behavior is unconfirmed. | Obtain written account-specific confirmation before implementation. |  | 2026-08-21 16:00
DEC-COUNTRIES | P04 | Initial launch country allowlist | Founder | 2026-08-06 16:00 | Blocked | Operating location is confirmed as Maryland, USA. Creator/member countries remain unanswered; eligibility and service coverage remain unresolved. | Use CCBill eligibility to narrow proposed creator/member countries. Obtain targeted legal review of unresolved country obligations before real launch. | docs/product/initial-business-definition.md — founder answers reviewed September 6, 2026 | 2026-08-21 16:00
DEC-ECONOMICS | P06 | Commission, payout and refund economics | Founder | 2026-08-13 16:00 | Blocked | Founder corrected the offer: Pumdoki should recover costs without profit on founding creator sales. Processing-fees-only is superseded. Duration, fee allocation and no-loss economics are unproven. | Validate processor costs, refunds, chargebacks, reserves and payout allocation before quoting fees. No-loss economics remain unproven. | docs/product/initial-business-definition.md — founder answers reviewed September 6, 2026 | 2026-09-09 16:00
DEC-RETENTION | P04 | Acceptance/evidence retention schedule | Founder | 2026-08-13 16:00 | Blocked | Retention, pseudonymization, lawful deletion, and litigation hold are undecided. | Obtain counsel-approved rules before deletion or operational creator onboarding. |  | 2026-08-21 16:00
DEC-OPS-ACCESS | P11 | Private-admin restricted access and hardware MFA | Founder | 2026-08-06 16:00 | Deferred | Slice 3 merged in PR #15. Provider-neutral dormant foundation exists; no operational provider/session/hosting activation. G1–G12 remain NOT EVALUATED. | Operations work remains parked. Next is the planned P05 test-content flow, pairing storage decisions with code. Actual spending, deployment and live sensitive-use controls remain. | https://github.com/QK-Connoisseur/PDoki/pull/15 | 2026-09-06 16:00
DEC-GWS-PRIVACY | P14 | Google Workspace recovery-contact privacy | Founder | 2026-08-20 16:00 | In Progress | Repository-safe checklist exists; private live review and independent recovery test remain. | Review private directory/recovery surfaces and test backup access without recording personal data in Git. | https://github.com/QK-Connoisseur/PDoki/tree/dev/docs/operations | 2026-08-21 16:00
QC-EXPENSE-Y1 | P00 | Expense Tracker Year 1 formula review | Engineering |  | Done | Corrected historical Year 1 arithmetic: 1,980 + 170 + 18 × 12 = 2,366. The old 1,713 is retained in Expense Tracker B38. Historical cost assumptions are superseded. | Use Launch Budget for current cash planning; replace allowances with accepted quotes in sequence. | Expense Tracker B33:B40; Launch Budget | 2026-09-06 16:00
DEC-SEQUENTIAL | P00 | Initial business definition and sequential workflow | Founder |  | Done | Business definition reviewed; founder works one functional slice at a time. Necessary founder/provider decisions accompany that slice rather than preceding all code as a paperwork phase. | R2 setup and safe-media integration verified. Next: founder reviews the working local upload/publish flow. No new provider signup, paperwork or payment task. Adult-content provider acceptance and hosted deployment remain unconfirmed. | September 9, 2026: credential preflight, real R2 API/browser photo/video tests, Cloudflare Public Access Disabled, restart and cleanup checks passed. Evidence: HANDOFF.md. Token expiry and budget alert are not verified. | 2026-09-09 16:00
DEC-LAUNCH-SCOPE | P00 | Discovery, real-time chat and tipping remain launch scope | Founder |  | Done | Connect is creator discovery filtered by online status, price and language. Real-time chat and tipping remain required. | Other confirmed launch scope remains. No automated booking expansion is implied. | Founder decision, September 6, 2026 | 2026-09-09 16:00
DEC-OASIS-CANCEL | P12 | Cancel the old Oasis/Drimy game | Founder |  | Done | The collectible pet/game, XP, Orbs, evolution, inventory and reward economy are cancelled. Historical prototype records are retained. | Do not build the old game or count it as a launch gate. | Founder decision, September 6, 2026 | 2026-09-06 16:00
DEC-OASIS-NEW | POST | Future streaks and playful language concept | Founder |  | Deferred | Oasis name may be reused for day/friend streaks and playful adult language/profanity learning, including optional roasting. This is a future concept, not the old game. | Define after launch. No implementation, paid randomized mechanics or new launch gate is approved. | Founder decision, September 6, 2026 | 2026-09-06 16:00
DEC-FOUNDING-OFFER | P06 | Founding creator acquisition and benefits | Founder |  | In Progress | Two contacts could help recruit 50–100 creators; these are prospects, not commitments. Founder badge and cost recovery with no profit on founder sales remain the direction. About 500 is a longer target. | Define first-cohort eligibility, countries, duration and cost allocation after counsel/processor fit. No-loss economics and Plus/top 100 benefits remain unproven. | docs/product/initial-business-definition.md — founder answers reviewed September 6, 2026 | 2026-09-06 16:00
DEC-PLUS-IDEAS | POST | Plus rewards, leaderboard and visual feedback | Founder |  | Deferred | Top 100 free Plus memberships, leaderboard, avatar decoration, animations, sounds and lively marketing are ideas. No reward cost/duration or entitlement promise is approved. | Revisit after core launch economics. Keep static themes; motion needs separate accessibility/performance review. | Founder direction, September 6, 2026 | 2026-09-06 16:00
DEC-CASH-20260906 | P00 | Frugal staged budget | Founder |  | In Progress | Founder now reports a $1,800 monthly ceiling and proposed recruiter/helper $300–$400/month. Inclusion in that ceiling and overlap with budget backup allowance are unconfirmed. Earlier cash assumptions remain. | Founder confirmed $196 Northwest formation and $1,100 policy drafting purchased on September 10. Actuals recorded in Expense Tracker; allowances unchanged. Monthly funding/helper overlap remains unresolved. | Founder funding statements September 6 and purchase confirmations September 10, 2026 | 2026-09-10 16:00
DEC-HUMAN-REVIEW | P14 | Human review timing and limited scopes | Founder |  | Ready | Use DIY work, suitable Fiverr specialists and drafts to control cost. Necessary legal work uses a qualified lawyer reviewing the actual model. Record the reviewed version, corrections and remaining limitations. | Use targeted reviews alongside relevant implementation and before live sensitive use. Controlled test implementation does not wait for blanket paid pre-code review. Independent integrated assessment and retest remain before real launch. | Founder correction, September 9, 2026: cancel proposed CCBill follow-up; develop functioning slices with relevant founder/provider work alongside code. PLAN.md §9 and §20 | 2026-09-08 16:00
DEC-LEGAL-UI-TRUTH | P04 | Truthful prototype legal UI and production replacement | Engineering |  | Done | Truthful prototype legal cleanup is pushed to dev in 56cb0ad. Local web219, contracts24, non-database API273 and builds passed. Production policies and processes remain unfinished. | Ship truthful placeholder copy with the next approved website release. Before public launch, counsel approves final policies and operators verify actual contacts/processes; deployment is separate from a Git merge. | https://github.com/QK-Connoisseur/PDoki/commit/56cb0adaffa4896aa9d54257b4eecfe18804bb54 | 2026-09-06 16:00

## Launch Budget
Pumdoki launch budget
September 10, 2026 |  |  | USD. Planning allowances, not quotes or permission to spend. Founder labor is unpaid.
Funding and cash needs | Lower case | Upper case | Meaning
Available now | 1000 | 5000 | Earlier total-cash assumption retained. New user-reported $1,800 monthly ceiling is not lump-sum cash or funded runway; sustainability is unconfirmed.
Possible additional cash | 5000 | 5000 | Uncommitted over coming months; excluded from funded cash.
Funded cash | 1000 | 5000 | Uses current cash only.
Setup incl. contingency | 8170.8 | 20469 | Includes discovery, scoped reviews, initial verification and first-year card registration benchmark.
Monthly operating allowance | 309 | 1179 | Small invited pilot; excludes transaction-linked expenses and annual renewals already paid in setup.
Runway months | 3 | 3 | Planning input; revenue is not assumed to cover costs.
Operating runway | 927 | 3537 | Monthly allowance × runway months.
Working cash buffer | 1000 | 3000 | Ring-fenced cash, not an expense or provider deposit quote. Does not cover an unknown processor reserve.
Baseline cash target | 10097.8 | 27006 | Setup + runway + working cash. Unknown deposits, processing/usage excesses, tax, insurance and professional requirements can raise this.
Gap using current cash | 9097.8 | 22006 | Positive amount needs more funding or a lower quoted scope before activation.
Gap if full $10k becomes funded | 97.8 | 17006 | Uses maximum current $5,000 + possible $5,000 later. Sensitivity only; additional cash is uncommitted.
Next: review the working local R2 flow |  |  | R2 connection verified. $0 was due at activation only; subsequent usage is metered. Proposed $5/month budget is not a hard cap. Budget-alert setup is unverified.
Low case is not a launch quote |  |  | Pilot counts remain planning assumptions. Two contacts may help recruit 50–100 creators; no committed cohort or creator/member countries were supplied.
Setup and review allowances | Lower case | Upper case | When / basis
Targeted legal advice allowance | 300 | 800 | Optional scoped advice for unresolved material issues. This allowance is separate from the purchased policy-document drafting bundle. Amount unchanged.
Targeted tax / accounting advice | 100 | 300 | Use when a specific tax or accounting question needs professional advice. Founder reports LLC filed; state approval pending. Unquoted allowance unchanged.
Initial advice allowances subtotal | 400 | 1100 | Reserve for necessary questions. This is not a required discovery purchase or a commitment to spend.
Entity, domain and admin setup | 250 | 900 | Founder confirmed $196 total paid to Northwest for Kiban Digital Holdings LLC. Maryland approval pending. Actual is in Expense Tracker; this planning allowance is unchanged.
Legal document drafting / review | 2000 | 6000 | Suzanne Lawyer on Fiverr hired for the $1,100 policy-document bundle. Delivery and substantive approval pending. Actual is in Expense Tracker; planning allowance unchanged.
Scoped architecture review | 500 | 1500 | Targeted backend/security review accompanies relevant code and precedes live sensitive use. No blanket paid pre-code review gate for controlled test implementation. Unquoted allowance unchanged.
Integrated security review + retest | 1500 | 5000 | Before real users, IDs, creator content or money. Independent scoped assessment of integrated system; quote may exceed allowance.
Visa high-risk annual registration | 950 | 950 | CCBill published benchmark, subject to account/region/category confirmation. First year included; renews annually.
Mastercard high-risk annual fee | 1000 | 1000 | CCBill US/Canada published benchmark; EU/UK page lists $500. Actual entity and underwriting determine applicability.
Initial creator verification batch | 99 | 250 | MAX(monthly minimum, invited creators × per-check allowance). Before the three operating months; repeats and extra performers add cost.
Fiverr buyer fee on tech reviews | 110 | 357.5 | 5.5% of the two technical review allowances. No split orders or purchases under $200 assumed; taxes extra.
Incremental setup subtotal | 6409 | 15957.5 | Excludes discovery subtotal. Professional service figures are allowances only.
Setup before contingency | 6809 | 17057.5 | Discovery + incremental setup.
Contingency rate | 20% | 20% | Planning allowance for scoped remediation and quote variance; not a completeness guarantee.
Contingency amount | 1361.8 | 3411.5
Setup including contingency | 8170.8 | 20469 | Founder coding time, household expenses and existing AI subscriptions excluded.
Monthly pilot allowance | Lower case | Upper case | What is included / unresolved
Compute, database, storage, backups | 75 | 250 | Planning allowance for small staging/production footprint. No free-tier expiry assumption. Actual service shape and adult-content terms unselected.
Email and monitoring tools | 10 | 30 | Allowance only. Choose provider later after business/provider fit and before external auth flows; no provider selected.
Bookkeeping / annual admin provision | 25 | 150 | Cash planning for records, filings and later tax advice; actual taxes and insurance are unpriced.
Identity provider monthly minimum | 99 | 149 | Benchmark only, not provider selection. Additional member age checks, new creators, rechecks and retention add variable cost.
Paid moderation / support backup | 100 | 600 | Proposed Discord recruiter/helper: $300–$400/month. Inclusion in $1,800 ceiling and overlap with this $100–$600 backup allowance are unconfirmed; no amount added. Scope/coverage remain unverified.
Monthly operating allowance | 309 | 1179 | Beyond pilot volume or founder capacity, replace with a staffing and usage quote before expanding.
Annual card renewal after year one | 1950 | 1950 | Already included in first-year setup; reserve for later renewal separately as dates become known.
Variable cost and cash obligations |  |  | Processor rate, fixed fees, refunds, chargebacks, payout/FX fees, member age checks, media processing/moderation and usage excesses: request quotes; no zero-cost assumption.
Processor hold / deposit |  |  | Unknown and excluded from target. A hold delays usable cash; a deposit ties up cash. Neither is ordinary spend unless lost or charged. Obtain amount, duration and release terms.
Founding creator offer |  |  | Founder correction: recover attributable costs without profit on founding creator sales. Processing-fees-only is superseded. Duration, cost allocation and no-loss economics are unproven; Plus revenue excluded.
Volume and fee inputs | Lower case | Upper case | Source / interpretation
Invited creator count | 25 | 100 | Unchanged planning counts. Two contacts could recruit 50–100 prospects, not commitments; ~500 remains the longer target.
Initial check unit allowance | 1.39 | 2.5 | Veriff Plus public benchmark $1.39; upper allowance includes pricing uncertainty. Neither establishes adult-platform suitability or required checks.
Initial minimum commitment | 99 | 149 | Veriff published Plus/Premium benchmarks. Terms and required plan must be confirmed; creator ID is not member age assurance.
Fiverr buyer service fee | 5.5% | 5.5% | Official standard buyer fee. Additional $3.50 on an order under $200; taxes and currency conversion may apply.
Sources checked September 6, 2026
CCBill card registration |  |  | https://ccbill.com/doc/risk-difference-between-low-risk-and-high-risk-accounts
CCBill pricing / underwriting |  |  | https://ccbill.com/pricing
Fiverr buyer fees |  |  | https://help.fiverr.com/hc/en-us/articles/37553933600657-Paying-for-orders-extras-or-custom-offers
Identity price benchmark |  |  | https://www.veriff.com/plans/self-serve
Storage price benchmark |  |  | https://developers.cloudflare.com/r2/pricing/
Compute price reference |  |  | https://aws.amazon.com/lightsail/pricing/
Professional / operating allowances |  |  | Planning allowances remain unquoted. Founder answers reviewed September 6, 2026 in initial-business-definition.md; new funding/helper statements are notes only, not formula changes.
Historic arithmetic |  |  | Expense Tracker historical estimates exclude the removed optional trademark line. Original displayed total 1,713 is retained. Confirmed purchases total $1,296; current planning remains separate.
Keep spending sequential |  |  | Fund and build one functional slice at a time. Pair necessary founder/provider decisions with code; next is test-content upload/publish/feed and storage. Spending/deployment/live-use controls remain. Financial assumptions unchanged.